## Project Types
Design/Implementation Block Grant (Year 2 Pilot) Eligible Project Types, Standards, Performance Measures Spreadsheet
Refer to Standard Milestones and Deliverables from Appendix 3 shown in "Milestones and Deliverables" tab. Links to references provided in footnotes
Sector | Eligible Project Types | Project Type Definition | Required Performance Measures | Required Project Standards | Match Requirements | Required Project Eligibility (in addition to general eligibility requirements specified in Project Selection & Screening Guidance Document) | Technical Support Contact Information
Forestry | Forestry - Final Design | Final design of forest logging road, trail, and/or stream crossing Acceptable Management Practices (AMPs) project(s) to address erosion to control nutrient and sediment pollution at prioritized locations. | Number of final (100%) designs completed | 1. Follow 2019 AMP Manual2 2. Follow 2019 Better Roads Standards3 | Not required, incentivized. | 1. Ensure projects are capital eligible (i.e. not assessment or project identification, must be eligible entity from Table 1 of Funding Policy1). 2. Discussed the project with Forest Parks and Recreation (Dave Wilcox) | Dave Wilcox, 802-476-0179, david.wilcox@vermont.gov
Forestry | Forestry - Implementation | Implementation of forest logging, road, trail, and/or stream crossing or Acceptable Management Practices (AMPs) project(s) to address erosion to control nutrient and/or sediment pollution at prioritized locations. | Linear feet of road drainage improved and/or Number of stream crossings improved | 1. Follow 2019 AMP Manual2 2. Follow 2019 Better Roads Standards3 | Not required, incentivized. | 1. Ensure projects are capital eligible (i.e. not assessment or project identification, must be eligible entity from Table 1 of Funding Policy1). 2. Discussed the project with Forest Parks and Recreation (Dave Wilcox) | Dave Wilcox, 802-476-0179, david.wilcox@vermont.gov
Lakes | Lake Shoreland – Preliminary Engineering Design | Preliminary determination of feasibility and design of lake shoreland restoration projects and lakeshore nutrient/sediment pollution reduction practices at priority locations. Work includes determining landowner interest, site/design considerations, permitting needs, and overall suitability for implementation practices. | Number of preliminary (30%) designs completed | 1. Follow shoreland best management practice standards 4 | Not required, incentivized | 1. Ensure projects are capital eligible (i.e. not assessment or project identification, must be eligible entity from Table 1 of Funding Policy1). 2. Contact the Lakes and Ponds Program before beginning the project for program approval and sign off (must document). | Amy Picotte, 802-490-6128, amy.picotte@vermont.gov
Lakes | Lake Shoreland – Final Engineering Design | Final design of lake shoreland restoration projects and/or lakeshore nutrient/sediment pollution reduction practices at priority locations. Work includes securing permit(s) and final operation and maintenance plan agreement(s). | Number of final (100%) designs completed | 1. Follow shoreland best management practice standards 4 | Not required, incentivized | 1. Ensure projects are capital eligible (i.e. not assessment or project identification, must be eligible entity from Table 1 of Funding Policy1). 2. Contact the Lakes and Ponds Program before beginning the project for program approval and sign off (must document). | Amy Picotte, 802-490-6128, amy.picotte@vermont.gov
Lakes | Lake Shoreland - Implementation | Implementation of lake shoreland restoration projects and/or lakeshore nutrient/sediment pollution reduction practices at priority locations. | Acres of lake shore restored and/or Linear feet of lake shore restored | 1. Follow shoreland best management practice standards. 4 2. Grantee must check in with the DEC Lakes and Ponds Program to identify applicable Lake Shoreland permits or obtain determination no permits are needed. | Not required, incentivized | 1. Ensure projects are capital eligible (i.e. not assessment or project identification, must be eligible entity from Table 1 of Funding Policy1). 2. Contact the Lakes and Ponds Program before beginning the project for program approval and sign off (must document). | Amy Picotte, 802-490-6128, amy.picotte@vermont.gov
Rivers | Rivers – Floodplain/Stream Restoration Preliminary Engineering Design | Preliminary determination of feasibility and design of stream/river and floodplain restoration projects to restore the stream/river to least erosion condition (i.e., equilibrium condition) and improve habitat. Restoration work includes removing/retrofitting river corridor/floodplain encroachments and instream structures. Work includes determining landowner interest, site/design considerations, permitting needs, and overall suitability for implementing project. | Number of preliminary (30%) designs completed. | 1. Grantee must check in with the DEC Regional River Scientist and obtain approval prior to each phase of a project: project initiation, scope of work development, 30% design, and 100% design phases. Check-ins must include submittal of project concepts/plans to date and discussion of project objectives and potential constraints. 2. Grantee must check in with the DEC Rivers Program to identify applicable floodplain, river corridor, or stream alteration permits or obtain determination no permits are needed. | Not required, incentivized | 1. Projects must be identified and ranked in a River Corridor Plan, Stream Geomorphic Assessment, or approved by Regional River Scientist. 2. Projects must meet the defined project types outlined in this spreadsheet. 3. Project must improve stream channel and/or floodplain connectivity. 4. Projects with larger scale/reach-scale benefits will have higher priority for funding and may be required to have a protection component to them (e.g., easement or other deed restriction) in addition to the typical operation and maintenance (O&M). 5. Projects must not create new conflicts with river/channel adjustments that may lead to increased channel management. 6. Projects must have documented DEC Regional River Scientist sign off on the project concept prior to awarding funds (within the timeline of the block grant). | Regional Rivers Scientist Contact5
Rivers | Rivers – Floodplain/Stream Restoration Final Engineering Design | Final design of stream/river and floodplain restoration projects to restore the stream/river to least erosion condition (i.e., equilibrium condition) and improve habitat. Restoration work includes removing retrofitting river corridor/floodplain encroachments and instream structures. Work includes securing permit(s) and final operation and maintenance plan agreement(s). | Number of final (100%) designs completed | 1. Grantee must check in with the DEC Regional River Scientist and obtain approval prior to each phase of a project: project initiation, scope of work development, 30% design, and 100% design phases. Check-ins must include submittal of project concepts/plans to date and discussion of project objectives and potential constraints. 2. Grantee must check in with the DEC Rivers Program to identify and obtain applicable floodplain, river corridor, or stream alteration permits prior to implementation or obtain determination no permits are needed. | Not required, incentivized | 1. Projects must be identified and ranked in a River Corridor Plan, Stream Geomorphic Assessment, or approved by Regional River Scientist. 2. Projects must meet the defined project types outlined in this spreadsheet. 3. Project must improve stream channel and/or floodplain connectivity. 4. Projects with larger scale/reach-scale benefits will have higher priority for funding and may be required to have a protection component to them (e.g., easement or other deed restriction) in addition to the typical operation and maintenance (O&M). 5. Projects must not create new conflicts with river/channel adjustments that may lead to increased channel management. 6. Projects must have documented DEC Regional River Scientist sign off on the project concept prior to awarding funds (within the timeline of the block grant). | Regional Rivers Scientist Contact5
Rivers | Rivers – Floodplain/Stream Restoration Implementation | Implementation of stream/river and floodplain restoration projects to restore the stream/river to least erosive condition (i.e., equilibrium condition) and improve habitat. Restoration work includes removing/retrofitting river corridor/floodplain encroachments and instream structures. Permits and operation and maintenance plan agreement(s) are in place prior to implementation. | 1. Floodplain restoration: Acres of floodplain reconnected/restored. 2. Stream restoration: linear feet of stream restored. 3. In-stream culvert work: stream miles reconnected for stream equilibrium/ aquatic organism passage. 4. Encroachment: number of river corridor/floodplain encroachments removed or retrofitted. | 1. Grantee must check in with the DEC Regional River Scientist and obtain approval prior to each phase of a project: project initiation, scope of work development, 30% design, and 100% design phases. Check-ins must include submittal of project concepts/plans to date and discussion of project objectives and potential constraints. 2. Grantee must obtain applicable floodplain, river corridor, or stream alteration permits prior to implementation or obtain confirmation no permits are needed. | Not required, incentivized | 1. Projects must be identified and ranked in a River Corridor Plan, Stream Geomorphic Assessment, or approved by Regional River Scientist. 2. Projects must meet the defined project types outlined in this spreadsheet. 3. Project must improve stream channel and/or floodplain connectivity. 4. Projects with larger scale/reach-scale benefits will have higher priority for funding and may be required to have a protection component to them (e.g., easement or other deed restriction) in addition to the typical operation and maintenance (O&M). 5. Projects must not create new conflicts with river/channel adjustments that may lead to increased channel management. 6. Projects must have documented DEC Regional River Scientist sign off on the project concept prior to awarding funds (within the timeline of the block grant). 7. All required permits must be secured prior to implementation, O&M agreement must be signed prior to close of project. | Regional Rivers Scientist Contact5
Stormwater | Stormwater – Preliminary Engineering Design | Preliminary determination of feasibility and design of stormwater management practice(s) that collect, store, infiltrate, and filter runoff that contains nutrient and sediment pollution from hard surfaces associated with developed/urban/suburban areas. Work includes determining landowner interest, site/design considerations, permitting needs, and overall suitability for project implementation. Work must result in at least 30% design of project which includes a design concept report, topographic and boundary survey, geotechnical report, and project drawings/specifications. | Number of preliminary (30%) designs completed. | 1. Must follow the 2017 stormwater manual for more technical aspects and guidance for design. 2. All projects should either provide treatment of the Water Quality Volume (1 inch, 24 hour storm), or if that is not possible due to site constraints, they must maximize treatment of runoff to the extent practicable. 3. Grantee must contact the DEC Stormwater Program to identify applicable operational or construction Stormwater permits or obtain determination no permits are needed. | 50% for identified MS4 communities (see RFP). All others, incentivized. | Eligible projects have been identified in an assessment or plan such as a Stormwater Master Plan (SWMP), Flow Restoration Plan or Phosphorus Control Plan, or have been approved by a Basin Planner. Assessment work (such as a SWMP) are ineligible. | Technical assistance 1. Hank Ainley, 802-490-6119, david.ainley@vermont.gov. 2. Helen Carr, 802-490-6170, helen.carr@vermont.gov. 3. Jim Pease, 802-490-6116, jim.pease@vermont.gov. Basin Planners: https://dec.vermont.gov/sites/dec/files/wsm/mapp/docs/TBP%20Contacts%20Map.pdf 6
Stormwater | Stormwater – Final Engineering Design | Final design of stormwater management practice(s) that collect, store, infiltrate, and filter runoff that contains nutrient and sediment pollution from hard surfaces associated with developed/urban/suburban areas. Work includes securing permit(s) and final operation and maintenance plan agreement(s). | Number of final (100%) designs completed | 1. Must follow the 2017 stormwater manual for more technical aspects and guidance for design. 2. All projects should either provide treatment of the Water Quality Volume (1 inch, 24 hour storm), or if that is not possible due to site constraints, they must maximize treatment of runoff to the extent practicable. 3. Grantee must contact the DEC Stormwater Program to identify and obtain applicable operational or construction stormwater permits prior to construction or obtain determination no permits are needed. | 50% for identified MS4 communities (see RFP). All others, incentivized. | Eligible projects have been identified in an assessment or plan such as a Stormwater Master Plan (SWMP), Flow Restoration Plan or Phosphorus Control Plan, or have been approved by a Basin Planner. Assessment work (such as a SWMP) are ineligible. | Technical assistance 1. Hank Ainley, 802-490-6119, david.ainley@vermont.gov. 2. Helen Carr, 802-490-6170, helen.carr@vermont.gov. 3. Jim Pease, 802-490-6116, jim.pease@vermont.gov. Basin Planners: https://dec.vermont.gov/sites/dec/files/wsm/mapp/docs/TBP%20Contacts%20Map.pdf 6
Stormwater | Stormwater – Project Implementation | Implementation of stormwater management practice(s) that collect, store, infiltrate, and filter runoff that contains nutrient and sediment pollution from hard surfaces associated with developed/urban/suburban areas. Permit(s) and operation and maintenance plan agreement(s) are in place prior to construction. | Acres of impervious surface treated and/or Acres of impervious area removed (if applicable) | 1. Must follow the 2017 stormwater manual for more technical aspects and guidance for design. 2. All projects should either provide treatment of the Water Quality Volume (1 inch, 24 hour storm), or if that is not possible due to site constraints, they must maximize treatment of runoff to the extent practicable. 3. Grantee must contact the DEC Stormwater Program to obtain applicable operational or construction stormwater permits prior to construction or obtain determination no permits are needed. | 50% for identified MS4 communities (see RFP). All others, incentivized. | Eligible projects have been identified in an assessment or plan such as a Stormwater Master Plan (SWMP), Flow Restoration Plan or Phosphorus Control Plan, or have been approved by a Basin Planner. Assessment work (such as a SWMP) are ineligible. | Technical assistance 1. Hank Ainley, 802-490-6119, david.ainley@vermont.gov. 2. Helen Carr, 802-490-6170, helen.carr@vermont.gov. 3. Jim Pease, 802-490-6116, jim.pease@vermont.gov. Basin Planners: https://dec.vermont.gov/sites/dec/files/wsm/mapp/docs/TBP%20Contacts%20Map.pdf 6
Wetlands | Wetland Restoration - Preliminary Engineering Design | Preliminary design to identify priority wetlands and buffer areas for restoration and protection work to promote water quality benefit, encourage flood resiliency, and provide habitat benefits. Work may include determining landowner/municipal interest, site/design considerations, permit needs, and overall suitability for implementing project. | Number of preliminary (30%) designs completed | Ensure all wetlands requirements are being met, resources available at: https://dec.vermont.gov/watershed/wetlands8 | Not required, incentivized. | No additional eligibility requirements. | Contact your wetland district ecologist7
Wetlands | Wetland Restoration - Final Engineering Design | Final design of wetland and buffer area restoration and protection projects to promote water quality benefit, encourage flood resiliency, and provide habitat benefits. Work may include securing permit(s) and operation and maintenance plan agreements, and final stewardship agreement(s). | Number of final (100%) designs completed | Ensure all wetlands requirements are being met, resources available at: https://dec.vermont.gov/watershed/wetlands8 | Not required, incentivized. | No additional eligibility requirements. | Contact your wetland district ecologist7
Wetlands | Wetland Restoration - Implementation | Implementation of wetland and buffer area restoration and protection projects to promote water quality benefit, encourage flood resiliency, and provide habitat benefits. | Acres of wetland restored | Ensure all wetlands requirements are being met, resources available at: https://dec.vermont.gov/watershed/wetlands8 | Not required, incentivized. | No additional eligibility requirements. | Contact your wetland district ecologist7
Referenced links
1 | CWIP Funding Policy https://dec.vermont.gov/sites/dec/files/WID/CWIP/2019-08-15_FINAL_FY20_CWIPFundingPolicy.pdf
2 | Follow 2019 AMP Manual (https://fpr.vermont.gov/sites/fpr/files/Forest_and_Forestry/Forest_Management/Library/FullDocument-7.29.pdf).
3 | Follow 2019 Better Roads Standards: https://vtrans.vermont.gov/sites/aot/files/highway/documents/ltf/Better%20Roads%20Manual%20Final%202019.pdf
4 | Follow shoreland best management practice standards: https://dec.vermont.gov/watershed/lakes-ponds/lakeshores-lake-wise/bmp.
5 | Contact your local rivers scientist: https://dec.vermont.gov/sites/dec/files/wsm/rivers/docs/rv_River_Scientist_Regions.pdf
6 | Basin Planners contact: https://dec.vermont.gov/sites/dec/files/wsm/mapp/docs/TBP%20Contacts%20Map.pdf
7 | Wetland District Ecologist https://dec.vermont.gov/watershed/wetlands/contact
8 | Wetlands requirements resources available at: https://dec.vermont.gov/watershed/wetlands

## Milestones&Deliverables
Forestry Sector | Milestones | Deliverables
Forestry – Design | Project initiated, ownership of site(s) identified | Locator map with site photo(s); summary of landowner contact
| Identified site/design considerations and permitting needs | Project summaries that identify site/design considerations, permitting needs, and water quality improvement needs and objectives
| Determination of O&M responsible party | Documentation of O&M responsible party once project is implemented
| 100% Design complete4 | Final Design Report (includes synthesis of prior completed project deliverables, 100% designs4, written landowner commitment to implement , and final cost-estimate
| Project complete | Final Performance Report3; press release
Forestry - Implementation | Project initiated; RFP issued and contractor selected (if applicable) | Copy of RFP and signed contract; statement of reasoning for contractor selection (if applicable); photo(s) of site(s) pre-implementation
| Implementation update(s); Clean Water Project Sign installed during construction if the project is considered publicly visible6. | Interim report(s) (includes summary of work to date, percent progress, and construction photos, including photo of Clean Water Project Sign, if applicable
Forestry acceptable management practice(s) implemented
| Project complete | Final Performance Report3; press release; post-implementation photo(s)
Lakes Sector | Milestones | Deliverables
Lake Shoreland - Preliminary Engineering Design | Project initiated; identified site/design considerations and permitting needs | Locator map with site photo(s); project summaries that identify site/design considerations, permitting needs, and restoration/water quality improvement objectives and goals
| 30% design complete4 | Preliminary Design Final Report (includes synthesis from prior completed project deliverables, 30% designs4, written landowner commitment to next project step, and cost-estimate)
| Project complete | Final Performance Report3; press release
Lake Shoreland - Final Engineering Design | Project initiated; determination of required permits | Documentation of required permits for project implementation, indicating potential challenges/conflicts for obtaining permit (if applicable) and project locator map
| Determination of O&M responsible party | Documentation of O&M responsible party once project is implemented
| 100% design complete4 | Final Design Report (includes synthesis of prior completed project deliverables, 100% designs4, written landowner commitment to implement project, and final cost-estimate)
| Project complete | Final Performance Report3; press release
Lake Shoreland – Implementation | Project initiated; RFP issued (if applicable) | Copy of RFP (if applicable); photo(s) of site(s) pre-implementation
| Contractor selected (if applicable) | Signed contract; statement of reasoning for contractor selection (if applicable)
| Required permits secured (if applicable) | Permit documentation (if applicable)
| Implementation update(s); Clean Water Project Sign installed during construction if the project is considered publicly visible6. | Interim report(s) (includes summary of work to date, percent progress, and construction photos, including photo of Clean Water Project Sign, if applicable)
Buffer restoration planting completed
| O&M plan created and signed | Signed 10-year (minimum) O&M Plan and Agreement Template (including timing and completion of plant protection removal if applicable)
| Project complete | Final Performance Report3 including buffer-BMP reporting; press release; post-implementation photo(s)
Rivers Sector | Milestones | Deliverables
Floodplain/Stream Restoration - Preliminary Engineering Design | Project initiated; ownership of site(s) identified | Locator map with site photo(s); summary of landowner contact
| Identified site/design considerations and permitting needs | Project summaries that identify site/design considerations, permitting needs, and restoration/water quality improvement objectives and needs (includes field survey completed with GIS-based map and cross-section locations)
| 30% design complete4 | Preliminary Design Final Report (includes alternatives analysis summary, synthesis of prior completed project deliverables, 30% designs4, written landowner commitment to next project step, and cost-estimates)
| Project complete | Final Performance Report3; press release
Floodplain/Stream Restoration - Final Engineering Design | Project initiated; determination of required permits | Documentation of required permits for project implementation, indicating potential challenges/conflicts for obtaining permit (if applicable) and project locator map
| Determination of O&M responsible party | Documentation of O&M responsible party once project is implemented
| 100% design complete4 | Final Design Report (includes synthesis of prior completed project deliverables, 100% designs4, written landowner commitment to implement project, and final cost-estimate)
| Project complete | Final Performance Report3; press release
Floodplain/Stream Restoration - Implementation | Project initiated; RFP issued (if applicable) | Copy of RFP (if applicable); photo(s) of site(s) pre-implementation
| Contractor selected (if applicable) | Signed contract; statement of reasoning for contractor selection (if applicable)
| Required permits secured (if applicable) | Permit documentation (if applicable)
| Implementation update(s); Clean Water Project Sign installed during construction if the project is considered publicly visible6. | Interim report(s) (includes summary of work to date, percent progress, and construction photos, including photo of Clean Water Project Sign, if applicable)
Floodplain/stream restoration project(s) implemented
| O&M plan created and signed | Signed 10-year (minimum) O&M Plan and Agreement Template
| Project complete | Final Performance Report3; press release; post-implementation photo(s)
Stormwater Sector | Milestones | Deliverables
Stormwater - Preliminary Engineering Design | Project initiated; ownership of site(s) identified | Locator map with site photo(s); summary of landowner contact
| Identified site/design considerations and permitting needs | Project summaries that identify site/design considerations, permitting needs, and water quality improvement objectives and goals
| 30% design complete4 | Preliminary Design Final Report (includes synthesis of prior completed project deliverables, 30% designs4, written landowner commitment to next project step, and cost-estimate)
| Project complete | Final Performance Report3 including BMP report(s) (one BMP report template for each 30% design completed); press release
Stormwater - Final Engineering Design | Project initiated; determination of required permits | Documentation of required permits for project implementation, indicating potential challenges/conflicts for obtaining permit (if applicable) and project locator map
| Determination of O&M responsible party | Documentation of O&M responsible party once project is implemented
| 100% design complete4 | Final Design Report (includes synthesis of prior completed project deliverables, 100% designs4, written landowner commitment to implement project, and final cost-estimate with a level of effort document)
| Project complete | Final Performance Report3 including BMP reporting (indicate BMP status as designed); press release
Stormwater – Implementation | Project initiated; RFP Issued (if applicable) | Copy of RFP (if applicable); photo(s) of site(s) pre-implementation
| Contractor selected (if applicable) | Signed contract; statement of reasoning for contractor selection (if applicable)
| Permit documentation (if applicable) | Required permits secured (if applicable)
| Implementation update(s); BMP(s) implemented, Clean Water Project Sign installed during construction if the project is considered publicly visible6. | Interim report(s) (includes summary of work to date, percent progress, construction photos, including Clean Water Project Sign photo, if applicable)
| O&M plan created and signed | Signed 10-year (minimum) O&M Plan and Agreement Template
| Project complete | Final Performance Report3 including BMP reporting (indicate BMP status as constructed); press release; post-implementation photo(s)
Wetlands Sector | Milestones | Deliverables
Wetland Restoration- Preliminary Engineering Design | Project initiated; ownership of site(s) identified | Locator map with site photo(s); summary of landowner contact
| Identified site/design considerations and permitting needs | Project summaries that identify site/design considerations, permitting needs, and restoration objectives and goals
| 30% design complete4 | Preliminary Design Final Report (includes synthesis of prior completed project deliverables, 30% designs4, written landowner commitment to next project step, and cost-estimate)
| Project complete | Final Performance Report3; press release
Wetland Restoration – Final Engineering Design | Project initiated; determination of required permits | Documentation of required permits for project implementation, indicating potential challenges/conflicts for obtaining permit (if applicable) and project locator map
| Determination of O&M responsible party | Documentation of O&M responsible party once project is implemented
| 100% design complete4 | Final Design Report (includes synthesis of prior completed project deliverables, 100% designs4, written landowner commitment to implement project, and final cost-estimate)
| Project complete | Final Performance Report3; press release
Wetland Restoration - Implementation | Project initiated; RFP issued (if applicable) | Copy of RFP (if applicable); photo(s) of site(s) pre-implementation
| Contractor selected (if applicable) | Signed contract; statement of reasoning for contractor selection (if applicable)
| Required permits secured (if applicable) | Permit documentation (if applicable)
| Implementation update(s); Clean Water Project Sign installed during construction if the project is considered publicly visible6. | Interim report(s) (includes summary of work to date, percent progress, and construction photos, including Clean Water Project Sign photo, if applicable)
BMP(s) implemented
| O&M plan created and signed | Signed 10-year (minimum) O&M Plan and Agreement Template
| Project complete | Final Performance Report3; press release; post-implementation photo(s)
End notes:
[1] The batch import file (BIF) is a required deliverable for assessment/planning projects resulting in project Identification. All projects involving project identification and prioritization are required to complete a table listing each project identified. The BIF is used to incorporate projects identified and prioritized into Vermont Tactical Basin Plan Implementation Tables and can be obtained from your technical grant manager.
[2] Locator maps for projects identified: Grantees/contractors are required to submit locator maps for each project identified under “project identification” projects, such as assessments and planning projects. Locator maps must be created using the ANR Atlas Ecosystem Restoration Grant Screening Layer (http://anrmaps.vermont.gov/websites/anra5/) so that potential indicators of natural resource conflicts/permitting needs will appear on the map of the project area. Project locator maps should be downloaded from the Atlas for each project identified and listed in the BIF (described above) and submitted as a PDF. See the Application Manual, Appendix 1, for instructions on how to create project locator maps.
[3] Final performance reports are the final deliverable for each Ecosystem Restoration grant/contract agreement (templates provided in Attachment E in all agreements). If a grant agreement involves stormwater design and project implementation, additional reporting at the best management practice (BMP) level may be required. Fillable formats of performance report templates are available at: http://dec.vermont.gov/watershed/cwi/grants.
[4] Ecosystem Restoration Design Terminology and Guidance Document defines design completion levels and expected deliverables and is available at: http://dec.vermont.gov/sites/dec/files/documents/ERPDesignTerminologyandGuidance.pdf.
[5] If both the grant manager and the engineer agree that topographic and boundary surveys and/or a geotechnical report are not necessary due to the nature of the dam removal location, instead provide a justification why they are not necessary. Grantee will not be paid for this deliverable if the surveys were not competed
[6] Clean Water Project signs are required on publicly visible implementation projects, if it is stated in their grant agreement and meets the requirements. 1. Signs should only be posted at publicly visible project implementation sites; 2. Signs should be posted during project construction if the duration of project construction is at least two weeks, or if duration of construction is less than two weeks, but the value of the project warrants signage; and 3. Signs cannot be posted in areas that may cause traffic hazards and signs must be located outside road right-of-way.A photo of the sign in place should be submitted with the deliverables. For more information click here: https://dec.vermont.gov/sites/dec/files/DEC-CWIP_CleanWaterProjectSignsGuidance_FINAL.pdf

## Sheet1 (hidden)
Requirements for all projects
1 | CWIP Funding Policy https://dec.vermont.gov/sites/dec/files/WID/CWIP/2019-08-15_FINAL_FY20_CWIPFundingPolicy.pdf
2 | Report performance measures based on project types as shown in Appendix 2.
3 | Refer to Standard Milestones and Deliverables by project type in Appendix 3.
4 | Follow 2019 AMP Manual (https://fpr.vermont.gov/sites/fpr/files/Forest_and_Forestry/Forest_Management/Library/FullDocument-7.29.pdf).
5 | Follow 2019 Better Roads Standards: https://vtrans.vermont.gov/sites/aot/files/highway/documents/ltf/Better%20Roads%20Manual%20Final%202019.pdf
6 | Work crew projects may not invoice multiple block grants, nor shall funds from one block grant be used as match for funds to another block grant.
7 | Follow shoreland best management practice standards: https://dec.vermont.gov/watershed/lakes-ponds/lakeshores-lake-wise/bmp.
8 | Contact your local rivers scientist: https://dec.vermont.gov/sites/dec/files/wsm/rivers/docs/rv_River_Scientist_Regions.pdf
9 | Basin Planners contact: https://dec.vermont.gov/sites/dec/files/wsm/mapp/docs/TBP%20Contacts%20Map.pdf
10 | Wetland District Ecologist https://dec.vermont.gov/watershed/wetlands/contact