## Appendix B (look here first)
Project Type | Funding Program | Definition | Performance Measures | Milestones | Deliverables | Step/Phase
Agricultural Pollution Prevention – Project Identification | RCPP | Assessments of agricultural lands (including cropland, pastureland, barnyards, and production areas) to target pollution prevention projects. These assessments identify areas with the highest contributions of pollutants. Work includes project identification and prioritization to target cost effective actions. | Acres assessed/covered by plan Number of projects identified | Project initiated; proposal/bid solicitations issued and contractor selected (if applicable) Site locations and boundaries identified Water quality improvement needs and objectives identified Prioritization criteria developed; project prioritization completed, highest priority projects identified Assessment complete Project complete | Documentation of problem areas with locator maps and site photo(s). Project summaries with water quality improvement needs and objectives identified List of criteria used for prioritization (must include level of landowner commitment); prioritized project list Final Assessment Report (includes synthesis from prior completed project deliverables); Batch Import File or ANR Online Clean Water Project - New Project Form (once available) Media announcement Final Performance Report or ANR Online Clean Water Project - Project Closeout Form (once available) | Assessment/Identification
Agricultural Pollution Prevention –Engineering Design | Formula, Enhancement (EDDIBG), DIBG (old) | Design of high priority agricultural best management practices, in alignment with NRCS Practice Standards (if applicable), that reduce pollutants (e.g., nutrients, pathogens, sediment) and improve soil health. Excludes riparian plantings on agricultural lands and annual agronomic practices. Project eligibility is limited to land where owner or operator is not required to meet the Required Agricultural Practices (RAPs). Work includes preparing permit application(s) and documentation of operation and maintenance plan(s.) More information: (https://www.nrcs.usda.gov/resources/guides-and-instructions/field-office-technical-guides) (https://agriculture.vermont.gov/rap) | Number of preliminary (30%) designs completed Number of final (100%) designs completed | Project initiated; proposal/bid solicitations issued and contractor selected (if applicable) Conceptual site plan drafted Stakeholder meetings Preliminary (30%) design complete (if applicable) Preliminary VDHP Project Review (if applicable) 10-year (minimum) DEC Operation and Maintenance (O&M) Plan drafted; refer to O&M manual for guidance 10-year (minimum) access license or easement (if applicable) drafted; refer to DEC template for guidance Other permit-required assessments or plans completed (if applicable) Final (100%) design complete Required permit applications drafted ** (Projects requiring a Wetlands Individual Permit must have this secured prior to the close of final design) Final VDHP Project Review (if applicable) Project complete | Draft 10-year (minimum) DEC Operation and Maintenance (O&M) Plan and documentation of support/commitment from O&M responsible party and landowner Draft 10-year (minimum) access license or easement and documentation of project support/commitment from landowner Draft permit application materials (including associated assessment reports or plans if applicable), wetlands individual permit (if applicable) Signed VDHP Project Review Form (if applicable) Final Design Report Media announcement Final Performance Report or ANR Online Clean Water Project - Project Closeout Form (once available) Batch Import File or ANR Online Clean Water Project - New Project Form (once available) | Final Design
Agricultural Pollution Prevention – Implementation | Formula, Enhancement (EDDIBG), DIBG (old) | Implementation of high priority agricultural best management practices, in alignment with NRCS Practice Standards (if applicable), that reduce pollutants (e.g., nutrients, pathogens, sediment) and improve soil health. Excludes riparian plantings on agricultural lands and annual agronomic practices. Project eligibility is limited to land where owner or operator is not required to meet the Required Agricultural Practices (RAPs). Permit(s), access license(s)/easement(s), and operation and maintenance plan(s) are in place prior to construction. More information: (https://www.nrcs.usda.gov/resources/guides-and-instructions/field-office-technical-guides) (https://agriculture.vermont.gov/rap) | Acres of agricultural land treated Linear feet of project implemented (for fencing or riparian projects) Number of projects completed (for structural, size neutral projects) | Project initiated 10-year (minimum) DEC Operation and Maintenance (O&M) Plan signed by O&M responsible party 10-year (minimum) access license or easement (if applicable) signed by landowner Proposal/bid solicitations issued, pre-bid site visits, and contractors selected/contracted (if applicable) Required permits secured Pre-construction kick-off meeting, walk through of the site with plans, evaluate any needs/issues/considerations for plan adjustments Clean Water Project Sign has been installed during construction if the project is considered publicly visible. Agricultural best management practice(s) (BMPs) implemented, final construction walkthrough Other permit-required activities completed or elements installed (if applicable), VDHP Treatment Plan implementation (if applicable) Return of Clean Water Project sign to host site (if applicable) Project complete | Photo(s) of site(s) pre-implementation Permit documentation (if applicable) Signed 10-year (minimum) DEC Operation and Maintenance Plan Signed 10-year (minimum) access license or easement As-built drawings or red-lined 100% designs with a list of change orders describing adjustments made during construction. Photo(s) of site(s) post-implementation, including photo of Clean Water Project Sign (if applicable) Media announcement Final Performance Report or ANR Online Clean Water Project - Project Closeout Form (once available) | Implementation
Road Erosion Inventory - Project Identification | LCBP | Inventory of hydrologically connected gravel and/or paved road segments in a road network to identify specific road erosion and drainage problems impacting water quality. Work includes identification of road-related erosion and drainage treatment practices to divert, collect, store, infiltrate, and/or filter runoff from transportation infrastructure (e.g., ditches, turnouts, check dams, culvert armoring). Work includes identification and prioritization of practices to target cost effective actions on road segments not/partially meeting Municipal Roads General Permit (MRGP) standards. Practices should be listed in the MRGP and designed to make the road segment(s)meet MRGP standards. The MRGP inventory may be adapted/adopted to non-municipal road networks (e.g., private roads, forest roads) for priority areas with DEC approval. More information: (https://dec.vermont.gov/watershed/stormwater/permit-information-applications-fees/municipal-roads-program) | Linear miles assessed/covered by plan Number of projects identified | Project initiated; proposal/bid solicitations issued and contractor selected (if applicable) Road network and boundaries identified, or site locations and boundaries identified. Road network segmented and GIS-determined hydrologically connected road segments identified. Road erosion inventory methodology and standards established (if applicable) Hydrologically connected road segments inventoried Road Erosion Inventory complete Cost-effective practices on road segments not/partially meeting standards prioritized Project complete | Implementation table of prioritized road segments requiring water quality improvements, including best management practices necessary to bring road segments into fully meeting standards and associated cost estimates. List of criteria used for prioritization (must include level of landowner commitment for non-municipal road networks). Batch Import File or ANR Online Clean Water Project - New Project Form (once available) Submit Road Erosion Inventory data to DEC in format requested Media announcement Final Performance Report or ANR Online Clean Water Project - Project Closeout Form (once available) - In notes section, please include summary of number of road segments assessed, number of segments not meeting, partially meeting and fully meeting standards, as well as synthesis of previous steps completed. | Assessment/Identification
Road Project – Preliminary Engineering Design | Formula, Enhancement (EDDIBG), MS4, DIBG (old) | Preliminary design of high priority road-related erosion and drainage treatment practices to divert, collect, store, infiltrate, and/or filter runoff from transportation infrastructure (e.g., ditches, turnouts, check dams, culvert armoring). Practices should be located on hydrologically connected gravel and/or paved road segments not/partially meeting Municipal Roads General Permit (MRGP) standards. Practices should be listed in the MRGP and designed to make the road segment(s)meet MRGP standards. Work must result in at least 30% design of project. Note that if a roads project includes a stream crossing improvement, the Floodplain/Stream Restoration project type should also be followed including applicable definitions, milestones, deliverables, and programmatic reviews. More information: (https://dec.vermont.gov/watershed/stormwater/permit-information-applications-fees/municipal-roads-program) | Number of preliminary (30%) designs completed | Project initiated; proposal/bid solicitations issued and contractor selected (if applicable) Conceptual site plan drafted Stakeholder meetings Other permit-required assessments or plans completed (if applicable) Preliminary (30%) design complete Preliminary VDHP Project Review (if applicable) Project complete | Signed VDHP Project Review Form (if applicable) Preliminary Design Report Media announcement Final Performance Report or ANR Online Clean Water Project - Project Closeout Form (once available) Batch Import File or ANR Online Clean Water Project - New Project Form (once available) | Preliminary Design
Road Project – Final Engineering Design | Formula, Enhancement (EDDIBG), MS4, DIBG (old) | Final design of high priority road-related erosion and drainage treatment practices to divert, collect, store, infiltrate, and/or filter runoff from transportation infrastructure (e.g., ditches, turnouts, check dams, culvert armoring). Practices should be located on hydrologically connected gravel and/or paved road segments not/partially meeting Municipal Roads General Permit (MRGP) standards. Practices should be listed in the MRGP and designed to make the road segment(s) meet MRGP standards. Work includes preparing permit application(s) and documentation of operation and maintenance plan(s.) Note that if a roads project includes a stream crossing improvement, the Floodplain/Stream Restoration project type should also be followed including applicable definitions, milestones, deliverables, and programmatic reviews. More information: (https://dec.vermont.gov/watershed/stormwater/permit-information-applications-fees/municipal-roads-program) | Number of final (100%) designs completed | Project initiated; proposal/bid solicitations issued and contractor selected (if applicable) Stakeholder meetings 10-year (minimum) DEC Operation and Maintenance (O&M) Plan drafted; refer to O&M manual for guidance 10-year (minimum) access license or easement (if applicable) drafted; refer to DEC template for guidance Other permit-required assessments or plans completed (if applicable) Final (100%) design complete Required permit applications drafted ** (Projects requiring a Wetlands Individual Permit must have this secured prior to the close of final design) Final VDHP Project Review (if applicable) Project complete | Draft 10-year (minimum) DEC Operation and Maintenance (O&M) Plan and documentation of support/commitment from O&M responsible party and landowner Draft 10-year (minimum) access license or easement and documentation of project support/commitment from landowner Draft permit application materials (including associated assessment reports or plans if applicable), wetlands individual permit (if applicable) Signed VDHP Project Review Form (if applicable) Final Design Report Media announcement Final Performance Report or ANR Online Clean Water Project - Project Closeout Form (once available) Batch Import File or ANR Online Clean Water Project - New Project Form (once available) | Final Design
Road Project – Implementation | Formula, Enhancement (EDDIBG),MS4, DIBG (old) | Implementation of high priority road-related erosion and drainage treatment practices to divert, collect, store, infiltrate, and/or filter runoff from transportation infrastructure (e.g., ditches, turnouts, check dams, culvert armoring). Practices should be located on hydrologically connected gravel and/or paved road segments not/partially meeting Municipal Roads General Permit (MRGP) standards. Practices should be listed in the MRGP and designed to make the road segment(s) meet MRGP standards. Road segments identified and improved in the absence of a local road erosion inventory (REI) must perform a pre and post segment assessment using the REI protocols. Permit(s), access license(s)/easement(s), and operation and maintenance plan(s) are in place prior to construction. Note that if a roads project includes a stream crossing improvement, the Floodplain/Stream Restoration project type should also be followed including applicable definitions, milestones, deliverables, and programmatic reviews. More information: (https://dec.vermont.gov/watershed/stormwater/permit-information-applications-fees/municipal-roads-program) | Number of drainage structures installed/repaired Linear feet of road drainage improved | Project initiated 10-year (minimum) DEC Operation and Maintenance (O&M) Plan signed by O&M responsible party 10-year (minimum) access license or easement (if applicable) signed by landowner Proposal/bid solicitations issued, pre-bid site visits, and contractors selected/contracted (if applicable) Required permits secured Pre-implementation REI assessment performed (if applicable) Pre-construction kick-off meeting, walk through of the site with plans, evaluate any needs/issues/considerations for plan adjustments Clean Water Project Sign installed during construction if the project is considered publicly visible. Road BMP(s) implemented, final construction walkthrough Post-implementation REI assessment performed (if applicable) Other permit-required activities completed or elements installed (if applicable), VDHP Treatment Plan implementation (if applicable) Return of Clean Water Project sign to host site (if applicable) Project complete | Photo(s) of site(s) pre-implementation Permit documentation (if applicable) Signed 10-year (minimum) DEC Operation and Maintenance Plan Signed 10-year (minimum) access license or easement As-built drawings or red-lined 100% designs with a list of change orders describing adjustments made during construction. Photo(s) of site(s) post-implementation, including photo of Clean Water Project Sign (if applicable) Media announcement Final Performance Report or ANR Online Clean Water Project - Project Closeout Form (once available) | Implementation
Stormwater/Road Equipment | MRGIA | Purchase of stormwater equipment with demonstrated water quality benefit to enhance/improve the application/installation of best management practices that will reduce erosion and control nutrient and sediment pollution (e.g. leaf blowers, roller compactors, hydro seeders). Requires establishment of long-term use and maintenance plan (minimum of ten years). If more than one entity, would require the establishment of an equipment share/rental program. | Hours equipment in use per year Linear feet of road drainage improved Road miles swept through use of equipment per year Acres stabilized through use of hydro seeder/mulcher equipment per year | Project initiated; purchase of equipment Cooperative agreement developed (if applicable) 10-year (minimum) DEC Operation and Maintenance (O&M) Plan drafted and signed; refer to O&M manual for guidance Project complete | Invoice for equipment purchase Signed cooperative agreement (if applicable); Signed 10-year (minimum) DEC Operation and Maintenance Plan Photo(s) showing equipment in use Transfer of Ownership Request letter Media announcement MRGIA Final Performance Report or ANR Online Clean Water Project - Project Closeout Form (once available) | Other
Stormwater – Illicit Discharge Detection and Elimination (IDDE) | IDDE | Illicit Discharge, Detection, and Elimination (IDDE) assessment to detect unauthorized/illicit discharges of wastewater or industrial process water into a stormwater-only drainage system. When illicit discharges are detected and confirmed, municipalities are required to address the illicit discharge, preventing wastewater or industrial process water from entering surface waters through stormwater-only infrastructure. | Number of illicit/unauthorized discharges confirmed | Project initiated; proposal/bid solicitations issued and contractor selected (if applicable) Data acquisition and review initiated Data acquisition and review completed IDDE assessment completed Project complete | Final report summarizing problems found, status of problems found, recommended actions, data tables, problem area maps, and cost-estimates Media announcement Final Performance Report or ANR Online Clean Water Project - Project Closeout Form (once available) | Other
Stormwater Master Plan - Project Identification | Formula, Enhancement (State) | Assessment of a geographic area (sub watershed or town) to determine where stormwater pollution is generated, and identify where it can be captured and removed efficiently by stormwater management practices that collect, store, infiltrate, and filter runoff that contains nutrient, sediment and/or other contaminant pollution from hard surfaces associated with developed/urban/suburban areas. Identified practices should be a listed Tier 1 or 2 practice in the most updated Stormwater Management Manual. Work includes identification and prioritization of practices to target cost effective actions that address/mitigate stormwater runoff, while preserving natural features and functions, with an emphasis on low impact green stormwater infrastructure. Prioritization must include use of Vermont's unified scoring matrix for Stormwater Master Plans. Focus must be on non-regulatory project opportunities. More information: (https://dec.vermont.gov/sites/dec/files/wsm/stormwater/docs/Permitinformation/2017%20VSMM_Rule_and_Design_Guidance_04172017.pdf) (https://dec.vermont.gov/water-investment/cwi/solutions/developed-lands/municipal-stormwater) | Acres assessed/covered by plan Number of projects identified | Project initiated; proposal/bid solicitations issued and contractor selected (if applicable) Desktop data acquisition and review completed Field assessments to identify existing condition water quality improvement needs and objectives Project prioritization completed Meeting(s) with stakeholders held Stormwater Master Plan completed Project complete | Data library Documentation of problem areas with locator maps and site photo(s). Project summaries with water quality improvement needs and objectives identified Prioritized project list completed using unified scoring matrix for Stormwater Master Plans Stormwater Master Plan (includes synthesis from prior completed project deliverables); Batch Import File or ANR Online Clean Water Project - New Project Form (once available) Media announcement Final Performance Report or ANR Online Clean Water Project - Project Closeout Form (once available) | Assessment/Identification
Stormwater – Preliminary Engineering Design | Formula, Enhancement (EDDIBG), MS4, DIBG (old) | Preliminary design of high priority Tier 1 or Tier 2 stormwater management practice(s) that collect, store, infiltrate, and filter runoff that contains nutrient, sediment and/or other contaminant pollution from hard surfaces associated with developed/urban/suburban areas. Work must result in at least 30% design of project. Refer to most updated Vermont Stormwater Management Manual for more information on Tier 1 and Tier 2 practices. More information: (https://dec.vermont.gov/sites/dec/files/wsm/stormwater/docs/Permitinformation/2017%20VSMM_Rule_and_Design_Guidance_04172017.pdf) | Number of preliminary (30%) designs completed | Project initiated; proposal/bid solicitations issued and contractor selected (if applicable) Conceptual site plan drafted Stakeholder meetings Other permit-required assessments or plans completed (if applicable) Preliminary (30%) design complete Preliminary VDHP Project Review (if applicable) Project complete | Signed VDHP Project Review Form (if applicable) Preliminary Design Report Media announcement Final Performance Report or ANR Online Clean Water Project - Project Closeout Form (once available) Batch Import File or ANR Online Clean Water Project - New Project Form (once available) | Preliminary Design
Stormwater – Final Engineering Design | Formula, Enhancement (EDDIBG), MS4, DIBG (old) | Final design of high priority Tier 1 or Tier 2 stormwater management practice(s) that collect, store, infiltrate, and filter runoff that contains nutrient, sediment and/or other contaminant pollution from hard surfaces associated with developed/urban/suburban areas. Work includes preparing permit application(s) and documentation of operation and maintenance plan(s). Refer to most updated Vermont Stormwater Management Manual for more information on Tier 1 and Tier 2 practices. More information: (https://dec.vermont.gov/sites/dec/files/wsm/stormwater/docs/Permitinformation/2017%20VSMM_Rule_and_Design_Guidance_04172017.pdf) | Number of final (100%) designs completed | Project initiated; proposal/bid solicitations issued and contractor selected (if applicable) Stakeholder meetings 10-year (minimum) DEC Operation and Maintenance (O&M) Plan drafted; refer to O&M manual for guidance 10-year (minimum) access license or easement (if applicable) drafted; refer to DEC template for guidance Other permit-required assessments or plans completed (if applicable) Final (100%) design complete Required permit applications drafted ** (Projects requiring a Wetlands Individual Permit must have this secured prior to the close of final design) Final VDHP Project Review (if applicable) Project complete | Draft 10-year (minimum) DEC Operation and Maintenance (O&M) Plan and documentation of support/commitment from O&M responsible party and landowner Draft 10-year (minimum) access license or easement and documentation of project support/commitment from landowner Draft permit application materials (including associated assessment reports or plans if applicable), wetlands individual permit (if applicable) Signed VDHP Project Review Form (if applicable) Final Design Report Media announcement Final Performance Report or ANR Online Clean Water Project - Project Closeout Form (once available) Batch Import File or ANR Online Clean Water Project - New Project Form (once available) | Final Design
Operational Stormwater Permit Obtainment | Green Schools | Design and permitting of stormwater management practice(s) to comply with Operational Stormwater Permit requirements (e.g., General Permit 3-9050 referred to as the “Three-Acre General Permit”) involving treatment of existing impervious surfaces. Project readiness for permitting can vary based on prior design work completed for the site, and 30%, 60%, and 100% design stages may not be required for all projects. | Number of preliminary (30%) designs completed (if applicable) Number of final (100%) designs completed (if applicable) Number of operational stormwater permits obtained | Project initiated; proposal/bid solicitations issued and contractor selected (if applicable) Identified site/design considerations Determination of additional required permits (e.g., wetland, floodplain) and preliminary review of feasibility of obtaining required permits Preliminary (30%) design complete (if applicable, depending on prior design work completed for project) 60% design complete (if applicable, depending on prior design work completed for project) Meeting(s) with landowner and other stakeholders to discuss planned projects and potential co-benefits (if applicable) Determination of O&M responsible party Final (100%) design complete (if applicable, depending on prior design work completed for project) Submission of permit application documentation to DEC Stormwater Program Project complete; permit obtained | Locator map(s) with site photos; letter of landowner commitment; project summaries that identify site/design considerations, natural resource constraints, water quality improvement objectives/goals, and natural resource constraints per the Engineering Feasibility Analysis criteria, including the existence of contaminated soil or groundwater Documentation of additional required permits for project implementation (include indication of potential challenges/conflicts for obtaining permit) Preliminary Design Report (includes synthesis of prior completed project deliverables, 30% designs, cost-estimates, and nutrient (and flow, if applicable) reduction estimates using STP Calculator) Intermediate Design Report (includes synthesis of prior completed project deliverables, 60% designs, cost-estimates, and nutrient (and flow, if applicable) reduction estimates using STP Calculator) Summary of meeting(s), including meeting outcomes, planned actions, and potential co-benefits Documentation of O&M responsible party once project is implemented; draft DEC Operation and Maintenance Plan and Agreement5 Final Design Report (includes synthesis of prior completed project deliverables, 100% designs, written landowner commitment to implement project, and final cost-estimate with a level-of-effort document) Completed application, site plans, and engineering feasibility analyses Media announcement Final Performance Report or ANR Online Clean Water Project - Project Closeout Form (once available) Batch Import File or ANR Online Clean Water Project - New Project Form (once available) Documentation of permit obtained | Final Design
Stormwater – Implementation | Formula, Enhancement (EDDIBG), MS4, Green Schools, DIBG (old) | Implementation of high priority Tier 1 or Tier 2 stormwater management practice(s) that collect, store, infiltrate, and filter runoff that contains nutrient, sediment and/or other contaminant pollution from existing impervious, hard (e.g., paved) surfaces associated with developed/urban/suburban areas. Permit(s), access license(s)/easement(s), and operation and maintenance plan(s) are in place prior to construction. Refer to most updated Vermont Stormwater Management Manual for more information on Tier 1 and Tier 2 practices. More information: (https://dec.vermont.gov/sites/dec/files/wsm/stormwater/docs/Permitinformation/2017%20VSMM_Rule_and_Design_Guidance_04172017.pdf) | Acres of impervious surface treated Acres of impervious area removed (if applicable) | Project initiated 10-year (minimum) DEC Operation and Maintenance (O&M) Plan signed by O&M responsible party 10-year (minimum) access license or easement (if applicable) signed by landowner Proposal/bid solicitations issued, pre-bid site visits, and contractors selected/contracted (if applicable) Required permits secured Pre-construction kick-off meeting, walk through of the site with plans, evaluate any needs/issues/considerations for plan adjustments Clean Water Project Sign installed during construction if the project is considered publicly visible Stormwater BMP(s) implemented, final construction walkthrough Other permit-required activities completed or elements installed (if applicable), VDHP Treatment Plan implementation (if applicable) Return of Clean Water Project sign to host site (if applicable) Project complete | Photo(s) of site(s) pre-implementation Permit documentation (if applicable) Signed 10-year (minimum) DEC Operation and Maintenance Plan Signed 10-year (minimum) access license or easement As-built drawings or red-lined 100% designs with a list of change orders describing adjustments made during construction. Photo(s) of site(s) post-implementation, including photo of Clean Water Project Sign (if applicable) Media announcement Final Performance Report or ANR Online Clean Water Project - Project Closeout Form (once available) Documentation of leverage (if applicable) Initial Statement of Compliance (if applicable) | Implementation
Roads/Stormwater Gully - Design | Formula, Enhancement (EDDIBG), MS4, DIBG (old) | Preliminary and final design of high priority practices that stabilize an eroding stormwater gully from outlet through a flow path to connection with a surface water. Outlet and gully stabilization projects restore eroding channels to a state where sediment loss is minimized or eliminated. Restoration techniques include but are not limited to rock aprons, plunge pools, riprap, step pools, check dams, armored turnouts, outlet headwalls, seeding/mulching, and vegetated or structural bank and slope stabilization techniques. Stormwater and road outlet gully channels must be caused or exacerbated by human activity that concentrates stormwater flow onto steep slopes and channels must not otherwise be considered intermittent or perennial streams by the DEC Rivers Program. Project must address upstream stormwater flow for in-gully work to be eligible. Work includes preparing permit application(s) and documentation of operation and maintenance plan(s). | Number of preliminary (30%) designs completed (if applicable) Number of final (100%) designs completed | Project initiated; proposal/bid solicitations issued and contractor selected (if applicable) Conceptual site plan drafted Stakeholder meetings Preliminary (30%) design complete (if applicable) Preliminary VDHP Project Review (if applicable) 10-year (minimum) DEC Operation and Maintenance (O&M) Plan drafted; refer to O&M manual for guidance 10-year (minimum) access license or easement (if applicable) drafted; refer to DEC template for guidance 60% design complete (if applicable) Other permit-required assessments or plans completed (if applicable) Final (100%) design complete Required permit applications drafted ** (Projects requiring a Wetlands Individual Permit must have this secured prior to the close of final design) Final VDHP Project Review (if applicable) Project complete | Draft 10-year (minimum) DEC Operation and Maintenance (O&M) Plan and documentation of support/commitment from O&M responsible party and landowner Draft 10-year (minimum) access license or easement and documentation of project support/commitment from landowner Draft permit application materials (including associated assessment reports or plans if applicable), wetlands individual permit (if applicable) Signed VDHP Project Review Form (if applicable) Final Design Report Media announcement Final Performance Report or ANR Online Clean Water Project - Project Closeout Form (once available) Batch Import File or ANR Online Clean Water Project - New Project Form (once available) | Final Design
Roads/Stormwater Gully - Implementation | Formula, Enhancement (EDDIBG), MS4, DIBG (old) | Implementation of high priority practices that stabilize an eroding stormwater gully from outlet through a flow path to connection with a surface water. Outlet and gully stabilization projects restore eroding channels to a state where sediment loss is minimized or eliminated. Restoration techniques include but are not limited to rock aprons, plunge pools, riprap, step pools, check dams, armored turnouts, outlet headwalls, seeding/mulching, and vegetated or structural bank and slope stabilization techniques. Stormwater and road outlet gully channels must be caused or exacerbated by human activity that concentrates stormwater flow onto steep slopes and channels must not otherwise be considered intermittent or perennial streams by the DEC Rivers Program. Project must address upstream stormwater flow for in-gully work to be eligible. Permit(s), access license(s)/easement(s), and operation and maintenance plan(s) are in place prior to construction. | Acres of impervious surface treated Acres of gully stabilized Cubic feet of gully erosion restored | Project initiated; 10-year (minimum) DEC Operation and Maintenance (O&M) Plan signed by O&M responsible party 10-year (minimum) access license or easement (if applicable) signed by landowner Proposal/bid solicitations issued, pre-bid site visits, and contractors selected/contracted (if applicable) Required permits secured Pre-construction kick-off meeting, walk through of the site with plans, evaluate any needs/issues/considerations for plan adjustments Clean Water Project Sign installed during construction if the project is considered publicly visible Stormwater BMP(s) implemented, final construction walkthrough Other permit-required activities completed or elements installed (if applicable), VDHP Treatment Plan implementation (if applicable) Return of Clean Water Project sign to host site (if applicable) Project complete | Photo(s) of site(s) pre-implementation Permit documentation (if applicable) Signed 10-year (minimum) DEC Operation and Maintenance Plan Signed 10-year (minimum) access license or easement As-built drawings or red-lined 100% designs with a list of change orders describing adjustments made during construction. Photo(s) of site(s) post-implementation, including photo of Clean Water Project Sign (if applicable) Media announcement Final Performance Report or ANR Online Clean Water Project - Project Closeout Form (once available) | Implementation
Forest Road Erosion Inventory - Project Identification | LCBP | Inventory of hydrologically connected forest logging roads, trails, and/or stream crossings to identify legacy erosion and stormwater drainage problems impacting water quality. Work includes identification of where implementing forestry Acceptable Management Practices (AMPs) would be most beneficial and cost-effective in order to reduce erosion to control nutrient and sediment pollution. Work includes identification and prioritization of practices to target cost effective actions. Practices should be listed in the forestry Acceptable Management Practices (AMPs).The MRGP inventory may be adapted/adopted to non-municipal road networks (e.g., private roads, forest roads) for priority areas with DEC approval. More information: (https://fpr.vermont.gov/forest/managing-your-woodlands/acceptable-management-practices) | Linear miles assessed/covered by plan Number of projects identified | Project initiated; proposal/bid solicitations issued and contractor selected (if applicable) Road network and boundaries identified, or site locations and boundaries identified. Road/trail network segmented and GIS-determined hydrologically connected segments identified. Road erosion inventory methodology and standards established (if applicable) Hydrologically connected road/trail segments inventoried Road Erosion Inventory complete Cost-effective practices on road/trail segments not/partially meeting standards prioritized Project complete | Implementation table of prioritized road/trail segments requiring water quality improvements, including best management practices necessary to bring road segments into fully meeting standards and associated cost estimates. List of criteria used for prioritization (must include level of landowner commitment for non-municipal road networks). Batch Import File or ANR Online Clean Water Project - New Project Form (once available) Submit Road Erosion Inventory data to DEC in format requested Media announcement Final Performance Report or ANR Online Clean Water Project - Project Closeout Form (once available) - In notes section, please include summary of number of road/trail segments assessed, number of segments not meeting, partially meeting and fully meeting standards, as well as synthesis of previous steps completed. | Assessment/Identification
Forestry – Design | Formula, Enhancement (EDDIBG), DIBG (old) | Final design of high priority Acceptable Management Practices (AMPs) to address legacy forest erosion from forest and logging roads, trails, and/or stream crossing to control nutrient and sediment pollution at prioritized locations. Work includes preparing permit application(s) and documentation of operation and maintenance plan(s). More information: (https://fpr.vermont.gov/forest/managing-your-woodlands/acceptable-management-practices) | Number of final (100%) designs completed | Project initiated; proposal/bid solicitations issued and contractor selected (if applicable) Conceptual site plan drafted Stakeholder meetings Preliminary (30%) design complete (if applicable) Preliminary VDHP Project Review (if applicable) 10-year (minimum) DEC Operation and Maintenance (O&M) Plan drafted; refer to O&M manual for guidance 10-year (minimum) access license or easement (if applicable) drafted; refer to DEC template for guidance Other permit-required assessments or plans completed (if applicable) Final (100%) design complete Required permit applications drafted ** (Projects requiring a Wetlands Individual Permit must have this secured prior to the close of final design) Final VDHP Project Review (if applicable) Project complete | Draft 10-year (minimum) DEC Operation and Maintenance (O&M) Plan and documentation of support/commitment from O&M responsible party and landowner Draft 10-year (minimum) access license or easement and documentation of project support/commitment from landowner Draft permit application materials (including associated assessment reports or plans if applicable), wetlands individual permit (if applicable) Signed VDHP Project Review Form (if applicable) Final Design Report Media announcement Final Performance Report or ANR Online Clean Water Project - Project Closeout Form (once available) Batch Import File or ANR Online Clean Water Project - New Project Form (once available) | Final Design
Forestry – Implementation | Formula, Enhancement (EDDIBG), DIBG (old) | Implementation of high priority Acceptable Management Practices (AMPs) to address legacy forest erosion from forest and logging roads, trails, and/or stream crossing to control nutrient and sediment pollution at prioritized locations. Permit(s), access license(s)/easement(s), and operation and maintenance plan(s) are in place prior to construction. More information: (https://fpr.vermont.gov/forest/managing-your-woodlands/acceptable-management-practices) | Linear feet of road drainage improved Number of stream crossings improved | Project initiated; 10-year (minimum) DEC Operation and Maintenance (O&M) Plan signed by O&M responsible party 10-year (minimum) access license or easement (if applicable) signed by landowner Proposal/bid solicitations issued, pre-bid site visits, and contractors selected/contracted (if applicable) Required permits secured Pre-construction kick-off meeting, walk through of the site with plans, evaluate any needs/issues/considerations for plan adjustments Clean Water Project Sign installed during construction if the project is considered publicly visible Forestry acceptable management practice(s) implemented, final construction walkthrough, post-implementation REI assessment submitted Other permit-required activities completed or elements installed (if applicable), VDHP Treatment Plan implementation (if applicable) Return of Clean Water Project sign to host site (if applicable) Project complete | Photo(s) of site(s) pre-implementation Permit documentation (if applicable) Signed 10-year (minimum) DEC Operation and Maintenance Plan Signed 10-year (minimum) access license or easement As-built drawings or red-lined 100% designs with a list of change orders describing adjustments made during construction. Photo(s) of site(s) post-implementation, including photo of Clean Water Project Sign (if applicable) Media announcement Final Performance Report or ANR Online Clean Water Project - Project Closeout Form (once available) | Implementation
Forestry – Equipment | Funded through the Vermont Department of Forests Parks and Recreation | Purchase or construction of forestry equipment with demonstrated water quality benefit to enhance/improve the implementation of Acceptable Management Practices (AMPs) on logging jobs in Vermont. The AMPs will address water quality concerns and reduce erosion to control nutrient and sediment pollution (e.g., portable skidder bridges that reduce erosion at stream crossings on forest/logging roads). | Number of stream crossings improved Number of stream crossings improved as result of Skidder Bridge Use | Project initiated; purchase of equipment Forester cooperative agreement developed (if applicable); 10-year (minimum) DEC Operation and Maintenance (O&M) Plan drafted and signed; refer to O&M manual for guidance Project complete | Invoice for equipment purchase Signed cooperative agreement (if applicable); Signed 10-year (minimum) DEC Operation and Maintenance Plan Photo(s) showing equipment in use Transfer of Ownership Request letter Media announcement Final Performance Report or ANR Online Clean Water Project - Project Closeout Form (once available) | Other
Lake Wise Assessments - Project Identification | Formula, Enhancement (State) | Property-level assessments of lake shorelands to identify areas with the highest levels of nutrient/sediment pollution and habitat degradation for targeting pollution prevention and natural resources restoration projects. Work includes project identification and prioritization to target cost effective actions. Identified structural practices should be listed in the Vermont Bioengineering Manual or otherwise have support from the Vermont DEC Lakes and Ponds Program. More information: (https://dec.vermont.gov/sites/dec/files/documents/BioEngineeringManual_Final.pdf) | Acres assessed/covered by plan Number of projects identified | Project initiated; proposal/bid solicitations issued and contractor selected (if applicable) Kickoff meeting with stakeholders (e.g., lake association) Site locations and boundaries for evaluation identified Lake Wise assessments complete Prioritization criteria developed; project prioritization completed Lake Wise Assessment plan complete Project complete | Documentation of problem areas with locator maps and site photo(s). Project summaries with water quality improvement needs and objectives identified; summary of landowner involvement List of criteria used for prioritization (must include level of landowner commitment); prioritized project list Lake Wise Assessment report (includes synthesis from prior completed project deliverables); Batch Import File or ANR Online Clean Water Project - New Project Form (once available) Media announcement Final Performance Report or ANR Online Clean Water Project - Project Closeout Form (once available) | Assessment/Identification
Lake Watershed Action Planning (LWAP) - Project Identification | Formula, Enhancement (State) | Lake watershed-scale assessment to identify the highest stressors that are resulting in water quality and habitat degradation. LWAP results in a prioritized list of projects and strategies to address the sources of pollution and habitat degradation identified in the assessment. | Acres assessed/covered by plan Number of projects identified | Project initiated, proposal/bid solicitations issued, and sub-contractor selected (if applicable), hold introductory meetings, develop work plans Develop LWAP Teams and hold kickoff meeting with stakeholders (e.g., lake association) Library of pre-existing data sources and relevant GIS layers created Lake Shoreland and Lake Wise Assessments complete (if applicable) LWAP Roadway Assessments complete (if applicable) Stream Geomorphic Assessment (SGA) Lite (VT DEC Phase 2 - Rapid Stream Assessment Protocol) or Stream Wise Assessments complete (if applicable) Project Scoping: Prioritization criteria developed; project prioritization completed Meetings with stakeholders to review project prioritization Restoration plans, including recommended BMPs, Conceptual Designs developed for a subset of prioritized projects, and regulatory reviews Lake Watershed Action Plan complete Present Completed LWAP to Stakeholders/Public Project complete | Work plan and timeline Watershed Data Library/Reference Section including maps and spatial analysis of field assessment site locations, ANR Locator Map of Watershed, maps with site photos of identified problems as outlined in the VT DEC Technical Guidelines. Project summaries identified through the Lake Shoreland and Lake Wise Assessments that identify site/design considerations, permitting needs, cost estimates, restoration/water quality improvement objectives and goals, and level of landowner commitment Description of the approach used for the roadway assessment section of the LWAP, as outlined in the VTDEC Technical Guidelines. Field inventory, locator map, and site photos of hydrologically connected road segments that do not, partially, and fully meet standards. Project summaries that identify site/design considerations, permitting needs, and best management practices necessary to bring road segments into fully meeting standards, associated cost estimates, and level of landowner commitment Report on reach prioritization method and landowner contact Completed SGA Lite Assessment (Phase 2 - Rapid Stream Assessment) if applicable Stream Wise assessment sheets if applicable Stream project summaries that identify site/design considerations, permitting needs, cost estimates, restoration/water quality improvement objectives and goals, and level of landowner commitment and locator maps with site photo(s) of identified problems List of shoreland owners interested in Lake Wise and Lake Wise assessments completed including summary of results, projects identified, and awards given. Complete project prioritization table with graphs and pie charts showing greatest threats to lake by sector, list of problem areas, list of criteria used for prioritization w/ level of landowner commitment, and stakeholder prioritization meeting minutes. Restoration plans of prioritized projects including synthesis of prior completed project deliverables, written landowner commitment to next project step, and refined permit and cost-estimates Lake Watershed Action Plan Final Report, including synthesis from prior completed project deliverables, and locator maps if projects identified Public Presentation, posted on DEC or Lake Association Website Batch Import File or ANR Online Clean Water Project - New Project Form (once available) Media announcement Final Performance Report or ANR Online Clean Water Project - Project Closeout Form (once available) | Assessment/Identification
Lake Shoreland – Preliminary Engineering Design | Formula, Enhancement (EDDIBG), DIBG (old) | Preliminary design of high priority lake shoreland habitat restoration projects and/or lakeshore nutrient/sediment pollution reduction structural practices at priority locations within 250 feet of a lake shore. Designed practices must be listed in the Vermont Bioengineering Manual, or otherwise have support from the Vermont DEC Lakes and Ponds Program. Work must result in at least 30% design of project. More information: (https://dec.vermont.gov/sites/dec/files/documents/BioEngineeringManual_Final.pdf) | Number of preliminary (30%) designs completed | Project initiated; proposal/bid solicitations issued and contractor selected (if applicable) Conceptual site plan drafted Stakeholder meetings DEC Programmatic Staff Engagement Other permit-required assessments or plans completed (if applicable) Preliminary (30%) design complete Preliminary VDHP Project Review Project complete | DEC programmatic staff comments on design Signed VDHP Project Review Form Preliminary Design Report Media announcement Final Performance Report or ANR Online Clean Water Project - Project Closeout Form (once available) Batch Import File or ANR Online Clean Water Project - New Project Form (once available) | Preliminary Design
Lake Shoreland – Final Engineering Design | Formula, Enhancement (EDDIBG), DIBG (old) | Final design of high priority lake shoreland habitat restoration projects and/or lakeshore nutrient/sediment pollution reduction structural practices at priority locations within 250 feet of a lake shore. Work includes preparing permit application(s) and documentation of operation and maintenance plan(s). Designed practices must be listed in the Vermont Bioengineering Manual or otherwise have support from the Vermont DEC Lakes and Ponds Program. More information: (https://dec.vermont.gov/sites/dec/files/documents/BioEngineeringManual_Final.pdf) | Number of final (100%) designs completed | Project initiated; proposal/bid solicitations issued and contractor selected (if applicable) Stakeholder meetings DEC Programmatic Staff Engagement 10-year (minimum) DEC Operation and Maintenance (O&M) Plan drafted; refer to O&M manual for guidance 10-year (minimum) access license or easement (if applicable) drafted; refer to DEC template for guidance Other permit-required assessments or plans completed (if applicable) Final (100%) design complete Required permit applications drafted ** (Projects requiring a Wetlands Individual Permit must have this secured prior to the close of final design) Final VDHP Project Review Project complete | Draft 10-year (minimum) DEC Operation and Maintenance (O&M) Plan and documentation of support/commitment from O&M responsible party and landowner Draft 10-year (minimum) access license or easement and documentation of project support/commitment from landowner Draft permit application materials (including associated assessment reports or plans if applicable), wetlands individual permit (if applicable) DEC programmatic staff comments on design Signed VDHP Project Review Form Final Design Report Media announcement Final Performance Report or ANR Online Clean Water Project - Project Closeout Form (once available) Batch Import File or ANR Online Clean Water Project - New Project Form (once available) | Final Design
Lake Shoreland – Implementation | Formula, Enhancement (EDDIBG), DIBG (old) | Implementation of high priority lake shoreland habitat restoration projects and/or lakeshore nutrient/sediment pollution reduction structural practices at priority locations, within 250 feet of a lake shore. Practices must be listed in the Vermont Bioengineering Manual or otherwise have support from the Vermont DEC Lakes and Ponds Program. Permit(s), access license(s)/easement(s), and operation and maintenance plan(s) are in place prior to construction. More information: (https://dec.vermont.gov/sites/dec/files/documents/BioEngineeringManual_Final.pdf) | Acres of lake shoreland restored Linear feet of lake shoreline restored | Project initiated; 10-year (minimum) DEC Operation and Maintenance (O&M) Plan signed by O&M responsible party 10-year (minimum) access license or easement (if applicable) signed by landowner Proposal/bid solicitations issued, pre-bid site visits, and contractors selected/contracted (if applicable) Required permits secured Pre-construction kick-off meeting, walk through of the site with plans, evaluate any needs/issues/considerations for plan adjustments Clean Water Project Sign installed during construction if the project is considered publicly visible Lake shoreland restoration completed, final construction walkthrough Other permit-required activities completed or elements installed (if applicable), VDHP Treatment Plan implementation (if applicable) Return of Clean Water Project sign to host site (if applicable) Project complete | Photo(s) of site(s) pre-implementation Permit documentation (if applicable) Signed 10-year (minimum) DEC Operation and Maintenance Plan Signed 10-year (minimum) access license or easement As-built drawings or red-lined 100% designs with a list of change orders describing adjustments made during construction. Photo(s) of site(s) post-implementation, including photo of Clean Water Project Sign (if applicable) Media announcement Final Performance Report or ANR Online Clean Water Project - Project Closeout Form (once available) | Implementation
Stream Geomorphic Assessment Phase 1 - Project Identification | Formula, Enhancement (State) | Remote sensing assessment of rivers/streams at the watershed scale to divide rivers/streams into reaches and provide an initial review of stream reach condition. May involve utilization of the Functioning Floodplains Initiative Tool. | Stream miles assessed/covered by plan | Project initiated; proposal/bid solicitations issued and contractor selected (if applicable) Baseline data created including stream reach breaks, meander center lines, and valley walls; Stream Geomorphic Assessment Tool run Data entered to the DEC SGA data management system Quality assurance check complete Phase 1 SGA complete Project complete | Electronic Stream Geomorphic Assessment Tool GIS project Notification of data entry to DEC SGA data management system Quality assurance report from database Final SGA Phase 1 Report (includes synthesis from prior completed project deliverables) Media announcement Final Performance Report or ANR Online Clean Water Project - Project Closeout Form (once available) | Assessment/Identification
Stream Geomorphic Assessment Phase 2 (River Corridor Plan) - Project Identification | Formula, Enhancement (State) | Field based assessments of stream reaches to determine current geomorphic and habitat conditions and to determine potential management needs and strategies to restore stream to least erosive form over time (i.e., equilibrium). Could be done in conjunction with a Phase 1 Stream Geomorphic Assessment. Work includes project identification and prioritization to target cost effective actions. | Stream miles assessed/covered by plan Number of projects identified | Project initiated; proposal/bid solicitations issued and contractor selected (if applicable) Steering committee established; Project identification meeting held (if applicable) Reaches selected from SGA Phase 1; landowner permission obtained Field work completed; data entered to DEC SGA system Quality assurance check complete River Corridor Plan drafted; prioritized projects (if applicable) Phase 2 SGA River Corridor Plan complete Project complete | Table of projects identified following Rivers Program-provided template Report on reach prioritization method and landowner contact Verification of data entry to DEC SGA data management system Quality assurance report from database, Updated Stream Geomorphic Assessment Tool GIS project and related shapefiles for Phase 2 valley walls. Draft River Corridor Plan including minimum of five project packets. Project packets should include documentation of problem areas with locator maps and site photo(s), project summaries with water quality improvement needs and objectives identified, cost-estimates and landowner commitment to next project steps. Final SGA Phase 2 River Corridor Plan report (includes synthesis from prior completed project deliverables) Batch Import File or ANR Online Clean Water Project - New Project Form (once available) Media announcement Final Performance Report or ANR Online Clean Water Project - Project Closeout Form (once available) | Assessment/Identification
Dam Removal- Project Identification | LCBP | Assessments of potential dam removal restoration sites to identify locations with impacts to longitudinal stream equilibrium, habitat degradation, and/or risk of dam failure leading to water quality impacts. This work is done outside of a Stream Geomorphic Assessment or River Corridor Planning process or as a follow up to that process. These assessments identify sites where dam restoration projects will be most beneficial in order to restore the stream/river to least erosive form over time (i.e., equilibrium condition) and improve habitat. Work includes project identification and prioritization to target cost effective actions. | Stream miles assessed/covered by plan Number of projects identified | Project initiated; proposal/bid solicitations issued and contractor selected (if applicable) Site visit and planning meeting Site location and boundaries identified Restoration needs and objectives identified Prioritization criteria developed; project prioritization completed Project complete | Locator maps of identified project area(s); narrative of how areas were identified Project summaries should include documentation restoration needs, water quality improvement goals and objectives identified, and next steps for the site List of criteria used for prioritization (must include level of landowner commitment); prioritized project list Batch Import File or ANR Online Clean Water Project - New Project Form (once available) Media announcement Final Performance Report or ANR Online Clean Water Project - Project Closeout Form (once available) | Assessment/Identification
Dam Removal – Preliminary Engineering Design | Formula, Enhancement (Dam removal DIBG) | Preliminary design of a high priority dam removal project to restore hydrologic connectivity of surface waters. May involve alternatives analysis. Work must result in at least 30% design of project. | Number of preliminary (30%) designs completed | Project initiated; proposal/bid solicitations issued and contractor selected (if applicable) Field and desktop research for feasibility factors Conceptual site plan drafted Stakeholder meetings DEC Programmatic Staff Engagement Other permit-required assessments or plans completed (if applicable) Preliminary (30%) design complete Preliminary VDHP Project Review Project complete | Feasibility factors report, conceptual site plan. DEC programmatic staff comments on design Signed VDHP Project Review Form Preliminary Design Report Media announcement Final Performance Report or ANR Online Clean Water Project - Project Closeout Form (once available) Batch Import File or ANR Online Clean Water Project - New Project Form (once available) | Preliminary Design
Dam Removal – Final Engineering Design | Formula, Enhancement (Dam removal DIBG) | Final design of high priority dam removal project to restore hydrologic connectivity of surface waters. Work includes preparing permit application(s) and documentation of operation and maintenance plan(s). | Number of final (100%) designs completed | Project initiated; proposal/bid solicitations issued and contractor selected (if applicable) Stakeholder meetings DEC Programmatic Staff Engagement 60% design complete (if applicable) 10-year (minimum) DEC Operation and Maintenance (O&M) Plan drafted; refer to O&M manual for guidance 10-year (minimum) access license or easement (if applicable) drafted; refer to DEC template for guidance Other permit-required assessments or plans completed (if applicable) Final (100%) design complete Required permit applications drafted ** (Projects requiring a Wetlands Individual Permit must have this secured prior to the close of final design) Final VDHP Project Review Project complete | Draft 10-year (minimum) DEC Operation and Maintenance (O&M) Plan and documentation of support/commitment from O&M responsible party and landowner Draft 10-year (minimum) access license or easement and documentation of project support/commitment from landowner Draft permit application materials (including associated assessment reports or plans if applicable), wetlands individual permit (if applicable) DEC programmatic staff comments on design Signed VDHP Project Review Form Final Design Report Media announcement Final Performance Report or ANR Online Clean Water Project - Project Closeout Form (once available) Batch Import File or ANR Online Clean Water Project - New Project Form (once available) | Final Design
Dam Removal – Implementation | Formula, Enhancement (Dam removal DIBG) | Implementation of high priority dam removal project to restore hydrologic connectivity of surface waters. Permit(s), access license(s)/easement(s), and operation and maintenance plan(s) are in place prior to construction. | Acres of floodplain restored Linear feet of stream restored Stream miles reconnected for stream equilibrium/aquatic organism passage | Project initiated; 10-year (minimum) DEC Operation and Maintenance (O&M) Plan signed by O&M responsible party 10-year (minimum) access license or easement (if applicable) signed by landowner Proposal/bid solicitations issued, pre-bid site visits, and contractors selected/contracted (if applicable) Required permits secured Pre-construction kick-off meeting, walk through of the site with plans, evaluate any needs/issues/considerations for plan adjustments Clean Water Project Sign installed during construction if the project is considered publicly visible. Dam removed; restoration work completed, final construction walkthrough Other permit-required activities completed or elements installed (if applicable), VDHP Treatment Plan implementation (if applicable) Return of Clean Water Project sign to host site (if applicable) Project complete | Photo(s) of site(s) pre-implementation Permit documentation (if applicable) Signed 10-year (minimum) DEC Operation and Maintenance Plan Signed 10-year (minimum) access license or easement As-built drawings or red-lined 100% designs with a list of change orders describing adjustments made during construction. Photo(s) of site(s) post-implementation, including photo of Clean Water Project Sign (if applicable) Media announcement Final Performance Report or ANR Online Clean Water Project - Project Closeout Form (once available) | Implementation
Floodplain/Stream Restoration – Preliminary Engineering Design | Formula, Enhancement (EDDIBG), DIBG (old) | Preliminary design of high priority stream/river and floodplain restoration projects to restore the stream/river to least erosive condition (i.e., equilibrium condition) and improve habitat. Restoration work includes channel/floodplain modification to improve equilibrium dimensions/connections OR removal/retrofit of river corridor/floodplain encroachments or instream structures. Work must result in at least 30% design of project. | Number of preliminary (30%) designs completed | Project initiated; proposal/bid solicitations issued and contractor selected (if applicable) Conceptual site plan drafted Stakeholder meetings DEC Programmatic Staff Engagement Other permit-required assessments or plans completed (if applicable) Preliminary (30%) design complete Preliminary VDHP Project Review Project complete | DEC programmatic staff comments on design Signed VDHP Project Review Form Preliminary Design Report Media announcement Final Performance Report or ANR Online Clean Water Project - Project Closeout Form (once available) Batch Import File or ANR Online Clean Water Project - New Project Form (once available) | Preliminary Design
Floodplain/Stream Restoration – Final Engineering Design | Formula, Enhancement (EDDIBG), DIBG (old) | Final design of high priority stream/river and floodplain restoration projects to restore the stream/river to least erosive condition (i.e., equilibrium condition) and improve habitat. Restoration work includes channel/ floodplain modification to improve equilibrium dimensions/ connections OR removal/ retrofit of river corridor/ floodplain encroachments or instream structures. Work includes preparing permit application(s) and documentation of operation and maintenance plan(s). | Number of final (100%) designs completed | Project initiated; proposal/bid solicitations issued and contractor selected (if applicable) Stakeholder meetings DEC Programmatic Staff Engagement 60% design complete (if applicable) 10-year (minimum) DEC Operation and Maintenance (O&M) Plan drafted; refer to O&M manual for guidance 10-year (minimum) access license or easement (if applicable) drafted; refer to DEC template for guidance Other permit-required assessments or plans completed (if applicable) Final (100%) design complete Required permit applications drafted** (Projects requiring a Wetlands Individual Permit must have this secured prior to the close of final design) Final VDHP Project Review Project complete | Draft 10-year (minimum) DEC Operation and Maintenance (O&M) Plan and documentation of support/commitment from O&M responsible party and landowner Draft 10-year (minimum) access license or easement and documentation of project support/commitment from landowner Draft permit application materials (including associated assessment reports or plans if applicable), wetlands individual permit (if applicable) DEC programmatic staff comments on design Signed VDHP Project Review Form Final Design Report Media announcement Final Performance Report or ANR Online Clean Water Project - Project Closeout Form (once available) Batch Import File or ANR Online Clean Water Project - New Project Form (once available) | Final Design
Floodplain/Stream Restoration – Implementation | Formula, Enhancement (EDDIBG), DIBG (old) | Implementation of high priority stream/river and floodplain restoration projects to restore the stream/river to least erosive condition (i.e., equilibrium condition) and improve habitat. Restoration work includes channel/ floodplain modification to improve equilibrium dimensions/ connections OR removal/ retrofit of river corridor/ floodplain encroachments or instream structures. Permit(s), access license(s)/easement(s), and operation and maintenance plan(s) are in place prior to construction. | For floodplain restoration: Acres of floodplain reconnected/restored For stream restoration: Linear feet of stream restored For in-stream culvert work: Stream miles reconnected for stream equilibrium/aquatic organism passage For encroachment: Number of river corridor/ floodplain encroachments removed or retrofitted | Project initiated 10-year (minimum) DEC Operation and Maintenance (O&M) Plan signed by O&M responsible party 10-year (minimum) access license or easement (if applicable) signed by landowner Proposal/bid solicitations issued, pre-bid site visits, and contractors selected/contracted (if applicable) Required permits secured Pre-construction kick-off meeting, walk through of the site with plans, evaluate any needs/issues/considerations for plan adjustments Clean Water Project Sign installed during construction if the project is considered publicly visible. Floodplain/stream restoration project(s) implemented, final construction walkthrough Other permit-required activities completed or elements installed (if applicable), VDHP Treatment Plan implementation (if applicable) Return of Clean Water Project sign to host site (if applicable) Project complete | Photo(s) of site(s) pre-implementation Permit documentation (if applicable) Signed 10-year (minimum) DEC Operation and Maintenance Plan Signed 10-year (minimum) access license or easement As-built drawings or red-lined 100% designs with a list of change orders describing adjustments made during construction. Photo(s) of site(s) post-implementation, including photo of Clean Water Project Sign (if applicable) Media announcement Final Performance Report or ANR Online Clean Water Project - Project Closeout Form (once available) | Implementation
River Corridor and Wetland Easement – Design | Formula, Enhancement - State | Evaluation of potential river corridor easement projects identified in an assessment that will remediate river instability that is responsible for erosion conflicts, increased sediment and nutrient loading, and a reduction in river habitat. Work includes determining landowner interest, site/design considerations, and overall suitability for participation in the River Corridor Easement Program. | Acres of river corridor and/or wetland scoped for easement Number of projects identified | Project initiated; RFP issued and contractor selected DEC River Scientist and/or Wetland Scientist (if applicable) approval secured for RCE and/or Wetland Easement work Ownership of site(s) identified Site plan; conservation documents drafted Landowner negotiations completed Town approval received (if applicable) Final draft agreement for easement completed Project complete | Confirmation site is RCE priority from regional River Scientist GIS site plan that includes: Preliminary project design elements – Site plan with preliminary River Corridor Easement boundaries; locations of areas of possible conflict and/or landowner need, locations of possible restoration/enhancement projects, locations of possible wetlands, stream crossing, and other features (if applicable) of interest Final copy of draft conservation documents that have been shared with landowner Report of landowner negotiations, including commitment to implementation and cost-estimate. For interested landowners - Complete landowner interview document to obtain information about flooding history and current and previous land management practice, etc. Letter from town supporting project (if applicable) Final draft agreement for easement Media announcement Final Performance Report or ANR Online Clean Water Project - Project Closeout Form (once available) | Other
River Corridor and Wetland Easement – Implementation | Formula, Enhancement - State | Protection in perpetuity of a high priority river corridor and wetlands. River Corridor Easements (RCEs) allow for passive restoration of channel stability by allowing natural erosive forces of the river to establish its least erosive form over time (i.e., equilibrium condition). Wetland Easements (WEs) allow for passive restoration and protection of wetlands that are currently or previously impacted by land use activities, or of high quality will insure long term protection. Requires implementation of land use practices promoting water quality and encouraging flood resilience: landowner sells channel management rights; no new structures/development can occur within the corridor; a 50-foot river buffer of native woody vegetation is established that moves with the river. | Acres of riparian corridor and/or wetland conserved Linear feet of riparian corridor conserved | Project initiated; RFP issued and contractor selected (if applicable) Purchase and sales agreement signed Property title search and insurance completed Property survey completed Easement closed, and long-term monitoring plan developed Stewardship agreement created and signed Project complete | Signed purchase and sales agreement Title report Property survey (paper and electronic) Copy of all legally filed documents signed by the grantee and landowner; MOU for stewarding river corridor easements between grantee and DEC; copy of easement with DEC as a third-party beneficiary Signed stewardship agreement Copy of the deposit slip into the Stewardship Endowment Fund within 30 days of State check date of the Stewardship payment (if applicable) Media announcement Final Performance Report or ANR Online Clean Water Project - Project Closeout Form (once available) | Implementation
Riparian Buffer Planting | Formula, Enhancement (WBBG) | Planting of native woody trees and shrubs within buffer area of rivers/streams, wetlands, and/or lakes. Planting results in a minimum average buffer width of 35-feet and a minimum density of 300 stems per acre. Buffer supports restoration of river corridor/floodplain, wetland and/or lakeshore, filters nutrient and sediment pollution from runoff, and provides habitat benefits. Includes riparian plantings on agricultural lands. Work includes site identification, planting plan development, materials sourcing, site preparation, and planting installation. Sites will be selected for their benefits to water quality and must meet approval of the State (local DEC River Scientist and Basin Planner). Sites will be stable, proximate to water, and high-priority. Permit(s), access license(s)/easement(s), and operation and maintenance plan(s) are in place prior to planting. | Acres of riparian corridor buffer planted/restored Linear feet of riparian corridor buffer planted/restored | Project initiated; proposal/bid solicitations issued and contractor selected (if applicable) Sites and constraints identified, DEC River Scientist and Basin Planner approval secured Developed planting plan (including species type, number, and estimated cost) in accordance with SGA or River Corridor Planning recommendations (if available) 10-year (minimum) DEC Operation and Maintenance (O&M) Plan drafted and signed; refer to O&M manual for guidance 10-year (minimum) access license or easement (if applicable) drafted and signed by landowner; refer to DEC template for guidance Clean Water Project Sign installed during construction if the project is considered publicly visible. Site preparation activities (if applicable) Buffer restoration planting completed Return of Clean Water Project sign to host site (if applicable) Project complete | Photo(s) of site(s) pre-implementation Signed 10-year (minimum) DEC Operation and Maintenance Plan and Agreement, including map of location of planting and final planting plan (species list and counts). Signed 10-year (minimum) access license or easement Photo(s) of site(s) post-implementation, including photo of Clean Water Project Sign (if applicable) Media announcement Final Performance Report or ANR Online Clean Water Project - Project Closeout Form (once available) | Implementation
Wetland Restoration –Project Identification | RCPP | Systematic utilization of the Wetland Restoration Potential layer, Functioning Floodplains Initiative tool, Class I wetland locations, or VRAM wetlands assessment to identify priority wetlands and buffer areas for restoration and protection work to promote water quality benefit, encourage flood resiliency, and provide habitat benefits. Assessments involve project identification and prioritization to target cost effective actions. | Acres assessed/covered by plan Number of projects identified | Project initiated; proposal/bid solicitations issued and contractor selected (if applicable) Site visit and planning meeting (if applicable) Site locations and boundaries identified Restoration needs and objectives identified Prioritization criteria developed; project prioritization completed Assessment completed Project complete | Locator map of identified problem area(s) and narrative on how areas were identified Project summaries with restoration needs and objectives identified List of criteria used for prioritization (must include level of landowner commitment); prioritized project list Final Assessment Report (includes synthesis from prior completed project deliverables); Batch Import File or ANR Online Clean Water Project - New Project Form (once available) Media announcement Final Performance Report or ANR Online Clean Water Project - Project Closeout Form (once available) | Assessment/Identification
Wetland Restoration – Preliminary Engineering Design | Formula, Enhancement (EDDIBG), DIBG (old) | Preliminary design of wetland and buffer area restoration and protection projects to promote water quality benefit, encourage flood resiliency, and provide habitat benefits. Work must result in at least 30% design of project. | Number of preliminary (30%) designs completed | Project initiated; proposal/bid solicitations issued and contractor selected (if applicable) Conceptual site plan drafted Stakeholder meetings DEC Programmatic Staff Engagement Other permit-required assessments or plans completed (if applicable) Preliminary (30%) design complete Preliminary VDHP Project Review Project complete | DEC programmatic staff comments on design Signed VDHP Project Review Form Preliminary Design Report Media announcement Final Performance Report or ANR Online Clean Water Project - Project Closeout Form (once available) Batch Import File or ANR Online Clean Water Project - New Project Form (once available) | Preliminary Design
Wetland Restoration – Final Engineering Design | Formula, Enhancement (EDDIBG), DIBG (old) | Final design of wetland and buffer area restoration and protection projects to promote water quality benefit, encourage flood resiliency, and provide habitat benefits. Work may include securing permit(s) and operation and maintenance plan agreements, and final stewardship agreement(s). | Number of final (100%) designs completed | Project initiated; proposal/bid solicitations issued and contractor selected (if applicable) Stakeholder meetings DEC Programmatic Staff Engagement 10-year (minimum) DEC Operation and Maintenance (O&M) Plan drafted; refer to O&M manual for guidance 10-year (minimum) access license or easement (if applicable) drafted; refer to DEC template for guidance Other permit-required assessments or plans completed (if applicable) Final (100%) design complete Required permit applications drafted** (Projects requiring a Wetlands Individual Permit must have this secured prior to the close of final design) Final VDHP Project Review Project complete | Draft 10-year (minimum) DEC Operation and Maintenance (O&M) Plan and documentation of support/commitment from O&M responsible party and landowner Draft 10-year (minimum) access license or easement and documentation of project support/commitment from landowner Draft permit application materials (including associated assessment reports or plans if applicable), wetlands individual permit (if applicable) DEC programmatic staff comments on design Signed VDHP Project Review Form Final Design Report Media announcement Final Performance Report or ANR Online Clean Water Project - Project Closeout Form (once available) Batch Import File or ANR Online Clean Water Project - New Project Form (once available) | Final Design
Wetland Restoration – Implementation | Formula, Enhancement (EDDIBG), DIBG (old) | Implementation of high priority wetland and buffer area restoration and protection projects to promote water quality benefit, encourage flood resiliency, and provide habitat benefits. Permit(s), access license(s)/easement(s), and operation and maintenance plan(s) are in place prior to construction. | Acres of wetland restored | Project initiated 10-year (minimum) DEC Operation and Maintenance (O&M) Plan signed by O&M responsible party 10-year (minimum) access license or easement (if applicable) signed by landowner Proposal/bid solicitations issued, pre-bid site visits, and contractors selected/contracted (if applicable) Required permits secured Pre-construction kick-off meeting, walk through of the site with plans, evaluate any needs/issues/considerations for plan adjustments Clean Water Project Sign installed during construction if the project is considered publicly visible. Wetland restoration complete, final construction walkthrough Other permit-required activities completed or elements installed (if applicable), VDHP Treatment Plan implementation (if applicable) Return of Clean Water Project sign to host site (if applicable) Project complete | Photo(s) of site(s) pre-implementation Permit documentation (if applicable) Signed 10-year (minimum) DEC Operation and Maintenance Plan Signed 10-year (minimum) access license or easement As-built drawings or red-lined 100% designs with a list of change orders describing adjustments made during construction. Photo(s) of site(s) post-implementation, including photo of Clean Water Project Sign (if applicable) Media announcement Final Performance Report or ANR Online Clean Water Project - Project Closeout Form (once available) | Implementation
Project Development | Enhancement (EDDIBG), Formula, PDBG (old) | Scoping work on any non-regulatory project type to determine feasibility, constraints, and overall suitability for implementing the project. This typically includes reviewing site assessments or other project identification tools and prioritized plans, conducting site visits, refining project scope and phasing, developing conceptual maps and drawings, estimating pollutant reduction benefits, confirming landowner/municipal interest, identification of – and possible engagement with – other stakeholders, partners, and likely concerned parties (e.g. neighbors, funders, regulators), identifying the prospective responsible operations and maintenance party, consulting with DEC staff, and determining project budget and permit needs (local, state and federal), natural and cultural resource constraints, co-benefits, and other project considerations, site constraints and feasibility factors (e.g. rights-of-way, infrastructure, invasive species presence, hazardous materials concerns) in advance of design or between design phases. | Number of projects explored for design and/or implementation | Project initiated A list of proposed projects to develop prioritized Ownership of site(s) identified and contacted Site visit(s) complete DEC staff consultations Identified site/design considerations and permitting needs Identification of supportive operation and maintenance (O&M) responsible party Project complete | Batch Import File or ANR Online Clean Water Project - New Project Form (once available) for any projects absent from the Watershed Projects Database. Project Development findings submitted to DEC in format requested | Development
Block Grants | Enhancement (Dam Removal DIBG, EDDIBG, WBBG), Formula, MS4, DIBG (old), PDBG (old) | Agreements in which an entity is selected to manage pass-through funds on behalf of the CWIP to fund the identification, development, design, implementation and/or operation and maintenance of clean water projects. Block grant holders (Funding Program Administrators) must ensure that sub-recipients complete and submit to the Funding Program Administrator all standard milestones and deliverables as listed by project type in the most current CWIP Funding Policy at time of sub-agreement execution. Funding Program Administrator must ensure that sub-recipients report on all standard performance measures as listed by project type in the most current CWIP Funding Policy at time of sub-agreement execution. Refer to block grant agreements for listings of which deliverables should be shared with DEC. | Enumerated within grant agreement documentation | Project initiated, proposal/bid solicitations issued Proposal/bid prioritization framework developed and applied, and sub-recipients selected/contracted (if applicable) Quarterly check-ins with Technical Project Manager to provide project progress updates Oversight of sub-recipient work QA/QC of sub-recipient project closeout data Project complete | Batch Import File or ANR Online Clean Water Project - New Project Form (once available) for any projects absent from the Watershed Projects Database. Funding decisions uploaded to Watershed Projects Database via ANR Online Clean Water Project - Project Update Form (once available) Collated sub-recipient deliverables based on project type Final Performance Report or notice of completed QA/QC of closed out projects in Watershed Projects Database (once available) Media announcement Equipment Ownership Request / Approval Form (if applicable) | Other
Work Crew Block Grants | WCBG | Utilization of work crews to increase implementation of priority clean water projects. | Enumerated within grant agreement documentation | Project initiated; sub-grantees approved; submit projects for DEC approval according to grant agreement Implementation projects approved Implementation update(s); Clean Water Project Sign installed during construction if the project is considered publicly visible. Report on developed implementation plans; signed landowner agreements Project complete | Sub-grantee approvals; project summaries, including site descriptions and locator maps1; photo(s) of site(s) pre-implementation Batch Import File or ANR Online Clean Water Project - New Project Form (once available) for any projects absent from the Watershed Projects Database. Interim report(s) (includes summary of work to date, percent progress, and construction photos, including Clean Water Project Sign photo, if applicable)Implementation plans; signed landowner agreement(s) with signed 10-year (minimum) DEC Operation and Maintenance Plan and Agreement Final Performance Report; press release; post-implementation photo(s); | Other
Operations and Maintenance | Formula, Enhancement (WBBG) | Operations, maintenance and stewardship activities performed on any clean water project type previously funded in whole or in part by DEC and registered within the Clean Water Project Explorer. Activities performed in compliance with the most current CWIP Operations and Maintenance Guidance Manual | Number of projects maintained to fully functioning Acres receiving enhanced survivorship treatment | Project initiated Maintenance Contractor selected Prioritized Maintenance conducted in alignment with O&M agreement Project complete | Final report containing: summary of what was accomplished, challenges encountered, estimated priorities and costs for O&M the following year. Equipment Ownership Request / Approval Form (if applicable) | Operation & Maintenance

## Project type table WPD
Project Type | Description | Sector | FED Step | ID | CWRF querry | http://anrgdb:6262/ReportServer/Pages/ReportViewer.aspx?/DEC/WSMD/Tracking/WPD-ProjectTypes&rs:Command=Render
Agricultural Pollution Prevention - Education & Outreach | Developing and/or disseminating material to educate the public on water quality issues in the agriculture sector and local and statewide initiatives to facilitate the protection, maintenance, enhancement, and restoration of water resources through behavioral change. | Agriculture |  | 82 | Date of querry | 2023-08-28
Agricultural Pollution Prevention - Equipment | Purchase of agricultural equipment with demonstrated water quality benefit to enhance/improve the application/installation of best management practices (e.g., no-till seeding systems and dragline manure injection systems) that reduce erosion and runoff containing pollutants (e.g., nutrients, pathogens, sediment) and improve soil health. May require establishment of long-term use and maintenance plan (minimum of ten years). May involve the establishment of an equipment share/rental program. | Agriculture | 3 | 36
Agricultural Pollution Prevention - Final Design | Final design of agricultural best management practices that reduce pollutants (e.g., nutrients, pathogens, sediment) and improve soil health. | Agriculture | 2 | 45
Agricultural Pollution Prevention - Identification | Assessments of agricultural lands (including cropland, pastureland, barnyards, and production areas) to target pollution prevention projects. These assessments identify areas with the highest contributions of pollutants. Work includes project development and prioritization to target cost effective actions. | Agriculture |  | 11
Agricultural Pollution Prevention - Implementation | Implementation of agricultural best management practices that reduce pollutants (e.g., nutrients, pathogens, sediment) and improve soil health. Funding for farmers to implement water quality-related capital improvements, such as production area improvements, manure management projects, farm equipment, and pasture management. | Agriculture | 3 | 9
Agricultural Pollution Prevention - Mapping and Analytical Support | Collection and analysis of geospatial data that supports and enhances planning and assessment efforts to identify and prioritize agricultural water quality related projects (e.g., Lidar, agriculture land use mapping). Does not include research projects. | Agriculture |  | 87
Agricultural Pollution Prevention - Organizational Capacity & Development | Financial assistance to support local partner organizational capacity and development of new programs to assist farmers, municipalities, and other landowners and land managers in development and implementation of clean water projects. | Agriculture |  | 88
Agricultural Pollution Prevention - Preliminary Design | Preliminary determination of feasibility and design of agricultural best management practices that reduce pollutants (e.g., nutrients, pathogens, sediment) and improve soil health. Work includes determining landowner interest, site/design considerations, and overall suitability in implementing agricultural BMPs. | Agriculture | 1 | 65
Agricultural Pollution Prevention - Research | Projects that assist in answering a question related to agricultural pollution prevention water quality issues, such as developing methods to account for agriculture-related projects or help to identify high priority water resource protection and restoration locations. | Agriculture |  | 86
Agricultural Pollution Prevention - Technical Assistance | Technical support to assist individuals and/or organizations with the development of projects related to the agriculture sector. | Agriculture |  | 83
Forestry - Design | Final design of forest logging road, trail, and/or stream crossing Acceptable Management Practices (AMPs) project(s) to address erosion to control nutrient and sediment pollution at prioritized locations. | Forest | 2 | 49
Forestry - Education & Outreach | Developing and/or disseminating material to educate the public on water quality issues in the forestry sector and local and statewide initiatives to facilitate the protection, maintenance, enhancement, and restoration of water resources through behavioral change. | Forest |  | 77
Forestry - Equipment | Purchase or construction of forestry equipment with demonstrated water quality benefit to enhance/improve the implementation of Acceptable Management Practices (AMPs) on logging jobs in Vermont. The AMPs will address water quality concerns and reduce erosion to control nutrient and sediment pollution (e.g., portable skidder bridges that reduce erosion at stream crossings on forest/logging roads). | Forest | 3 | 64
Forestry - Identification | Assessments of forest logging roads, trails, and/or stream crossings to identify areas with the highest levels of erosion and nutrient and sediment pollution. These assessments identify project areas and prioritize project strategies to address where implementing forestry Acceptable Management Practices (AMPs) would be most beneficial and cost-effective in order to reduce erosion to control nutrient and sediment pollution. | Forest |  | 12
Forestry - Implementation | Implementation of forest logging road, trail, and/or stream crossing Acceptable Management Practices (AMPs) project(s) to address erosion to control nutrient and sediment pollution at prioritized locations. | Forest | 3 | 48
Forestry - Research | Projects that assist in answering a question related to forest land restoration, such as developing methods to account for forestry projects, or help to identify high priority water resource protection and restoration locations. | Forest |  | 97
In-Lake Treatment- Final Design | Final design of in-lake treatment practices that will reduce the effects of pollutants in a lake. | Lake | 2 | 71
In-Lake Treatment- Implementation | Implementation of in-lake treatment practices that will reduce the effects of pollutants in a lake. | Lake | 3 | 72
In-Lake Treatment- Preliminary Design | Preliminary determination of feasibility and design of in-lake treatment practices to reduce effects of nutrients and sediment in a lake. | Lake | 1 | 70
Lake Shoreland - Education & Outreach | Developing and/or disseminating material to educate the public on water quality issues in the lakes sector and local and statewide initiatives to facilitate the protection, maintenance, enhancement, and restoration of water resources through behavioral change. | Lake |  | 78
Lake Shoreland - Final Design | Final design of lake shoreland restoration projects and/or lakeshore nutrient/sediment pollution reduction practices at priority locations. Work includes securing permit(s) and final operation and maintenance plan agreement(s). | Lake | 2 | 51
Lake Shoreland - Identification | Assessments of lake shorelands to identify areas with the highest levels of nutrient/sediment pollution and habitat degradation for targeting pollution prevention and natural resources restoration projects. Work includes project development and prioritization to target cost effective actions. | Lake |  | 14
Lake Shoreland - Implementation | Implementation of lake shoreland restoration projects and/or lakeshore nutrient/sediment pollution reduction practices at priority locations. | Lake | 3 | 50
Lake Shoreland - Preliminary Design | Preliminary determination of feasibility and design of lake shoreland restoration projects and lakeshore nutrient/sediment pollution reduction practices at priority locations. Work includes determining landowner interest, site/design considerations, permitting needs, and overall suitability for implementing practices. | Lake | 1 | 66
Lake Watershed Action Plan | Assessment to identify the highest nutrient/sediment pollution loading areas of the lake watershed that are resulting in water quality and habitat degradation. The LWAP results in a prioritized list of projects and strategies to address the sources of pollution and habitat degradation identified in the assessment. The plan may also contain recommendations to preserve natural features and functions, encourage use of low impact green stormwater infrastructure, and maintain the aesthetic and recreational uses of lakes. | Lake |  | 95
Hazard Mitigation | Projects (that do not fit under another project category) that address hazard avoidance, public safety, pollution prevention, and/or flood resiliency. | Other |  | 68
Invasive Species Control | Targeted effort to identify, manage, or eradicate invasive species that have a direct negative impact on aquatic habitat or water quality. This involves invasive species assessments, spread prevention, or control projects. | Other | 3 | 40
Mapping and Analytical Support | Collection and analysis of geospatial data that supports and enhances planning and assessment efforts to identify and prioritize clean water projects across sectors. Does not include research projects or studies. | Other |  | 73
Multi Sector Block Grant | Represents a block grant "Parent" or "Umbrella" project. This project contains multiple child projects that are managed by one outside entity. Child projects may be from a variety of sectors. | Other |  | 75
Organizational Capacity and Development | Financial assistance to support local partner organizational capacity and development of new programs | Other |  | 101
Pollution Prevention, Abatement, and Mitigation | Projects that address surface water pollutants (such as toxics and pathogens) and/or legacy pollutants that are identified through monitoring and are not nutrient or sediment related. This category also includes projects that reduce or prevent the use of products that could result in the reduction of a pollutant as a by-product. | Other |  | 52
Project Development | Scoping work on any non-regulatory project type to determine feasibility, constraints, and overall suitability for implementing the project. This typically includes reviewing site assessments or other project identification tools and prioritized plans, conducting site visits, refining project scope and phasing, developing conceptual maps and drawings, estimating pollutant reduction benefits, confirming landowner/municipal interest, identification of – and possible engagement with - other stakeholders, partners, and likely concerned parties (e.g. neighbors, funders, regulators), identifying the responsible Operations and Maintenance party, consulting with DEC staff, and determining project budget and permit needs (local, state and federal), natural and cultural resource constraints, co-benefits, and other project considerations, site constraints and feasibility factors (e.g. rights-of-way, infrastructure, invasive species presence, hazardous materials concerns) in advance of design or between design phases. | Other |  | 102
Tactical Basin Planning Support Services | Participation in the development and execution of tactical basin plans as set forth in 10 VSA 1253(e). Statutory partners in the Tactical Basin Planning process utilize this grant funding to provide education, outreach, and technical assistance to municipalities and landowners, and identify opportunities for strategic partnerships in order to develop coordinated work plans to ensure Basin Planning tasks, services, and activities are coordinated regionally on the major planning basin scale (each of the 15 basins). | Other |  | 96
Water Quality Sampling | Water quality sampling project to monitor, identify, and track water resource pollutants as well as identify high quality waters. | Other |  | 39
Water Resource Protection | Protection of water resources that provide ecosystem services or are of high quality and threatened by development (not otherwise associated with any other categories). Protection areas may include, but are not limited to public fishing and boating access sites, public swimming holes, important water resources and undeveloped land adjacent to important water resources. Protection types include but are not limited to land acquisition, and reclassification of waters and wetlands. | Other |  | 44
Cross-sector Education & Outreach | Developing and/or disseminating material to educate the public on water quality issues and local and statewide initiatives to facilitate the protection, maintenance, enhancement, and restoration of water resources through behavioral change. | Outreach |  | 17
Cross-sector Technical Assistance | Technical support to assist individuals and/or organizations with the development of projects. | Outreach |  | 18
Cross-sector Research | Projects that identify water quality issues or other water resource conditions across sectors for purpose of identifying high priority water resource protection and restoration locations. | Research |  | 21
Dam Removal - Final Design | Final design of dam removal project to restore hydrologic connectivity of surface waters. Work includes obtaining any permits required. | River | 2 | 46
Dam Removal - Identification | Assessments of potential dam removal restoration sites to identify locations with impacts to longitudinal stream equilibrium, habitat degradation, and/or risk of dam failure leading to water quality impacts. This work is done outside of a Stream Geomorphic Assessment or River Corridor Planning Process or as a follow up to that process. These assessments identify sites where dam restoration projects will be most beneficial in order to and restore the stream/river to least erosive form over time (i.e., equilibrium condition) and improve habitat. Work includes project development and prioritization to target cost effective actions. | River |  | 99
Dam Removal - Implementation | Implementation of dam removal project to restore hydrologic connectivity of surface waters. Permits, operation and maintenance plans, and stewardship agreements(s) are in place prior to construction. | River | 3 | 47
Dam Removal - Preliminary Design | Preliminary determination of feasibility and design of a dam removal project to restore hydrologic connectivity of surface waters. Work includes determining landowner interest, site/design considerations, permitting needs, and overall suitability for implementing project. May involve feasibility or alternatives analysis. | River | 1 | 38
Floodplain/Stream Restoration - Final Design | Final design of stream/river and floodplain restoration projects to restore the stream/river to least erosive condition (i.e., equilibrium condition) and improve habitat. Restoration work includes channel/ floodplain modification to improve equilibrium dimensions/ connections OR removal/ retrofit of river corridor/ floodplain encroachments or instream structures. Work includes securing permit(s) and final operation and maintenance plan agreement(s). | River | 2 | 61
Floodplain/Stream Restoration - Implementation | Implementation of stream/river and floodplain restoration projects to restore the stream/river to least erosive condition (i.e., equilibrium condition) and improve habitat. Restoration work includes channel/ floodplain modification to improve equilibrium dimensions/ connections OR removal/ retrofit of river corridor/ floodplain encroachments or instream structures. Permits and operation and maintenance plan agreement(s) are in place prior to implementation. | River | 3 | 62
Floodplain/Stream Restoration - Preliminary Design | Preliminary determination of feasibility and design of stream/river and floodplain restoration projects to restore the stream/river to least erosive condition (i.e., equilibrium condition) and improve habitat. Restoration work involves, but is not limited to: 1) removing/retrofiting river corridor/floodplain encroachments and instream structures (e.g., bridges, abutments, roads, railroads, gravel/macadam/paved paths, utilities, buildings, parking lots, and fill) to restore space for equilibrium stream planform, floodplain access and function, sediment continuity and/or hydrologic connectivity of surface waters; and 2) instream projects (e.g., the removal of bank armoring, berms, floodwalls) to create and/or improve stream equilibrium and/or habitat features. Work includes determining landowner interest, site/design considerations, permitting needs, and overall suitability for implementing project. | River | 1 | 6
River - Mapping and Analytical Support | Collection and analysis of geospatial data that supports and enhances planning and assessment efforts to identify and prioritize river/stream/floodplain related projects (e.g., Lidar, impervious surface mapping). Does not include research projects. | River |  | 90
River - Planting | Planting of riparian buffer area along rivers/streams with trees and shrubs, resulting in an average minimum buffer width of 35-feet (300 stems per acre) , planted with native woody vegetation whose location floats with the river. Buffer supports restoration of riparian corridor/floodplain, filters nutrient and sediment pollution from runoff, and provides habitat benefits. | River | 3 | 5
River - Research | Projects that assist in answering a question related to river restoration, river corridor and floodplain issues, such as developing methods to account for rivers-related projects, or help to identify high priority water resource protection and restoration locations. | River |  | 91
River Corridor Easement - Design | Evaluation of potential river corridor easement projects identified in an assessment that will remediate river instability that is responsible for erosion conflicts, increased sediment and nutrient loading, and a reduction in river habitat. Work includes determining landowner interest, site/design considerations, and overall suitability for participation in the River Corridor Easement Program. | River | 2 | 57
River Corridor Easement - Implementation | Protection in perpetuity of a high priority river corridor to allow for passive restoration of channel stability by allowing natural erosive forces of the river to establish its least erosive form over time (i.e., equilibrium condition). Requires implementation of land use practices promoting water quality and encouraging flood resilience: landowner sells channel management; no new structures/development can occur within the corridor; a 50-foot riparian buffer of native woody vegetation is established that moves with the river. | River | 3 | 7
River Corridor Plan | Plan developed to identify and prioritize projects to remediate river instability that is responsible for erosion conflicts, increased sediment and nutrient loading, and a reduction in river habitat. Results in a prioritized list of projects and strategies to address problem areas. Could be done in conjunction with a Stream Geomorphic Assessment. | River |  | 2
River Project - Identification | Assessments of potential floodplain/stream restoration areas to identify locations with the highest levels of erosion, nutrient and sediment pollution, and/or habitat degradation. This work is done outside of a Stream Geomorphic Assessment or River Corridor Planning Process or as a follow up to that process. These assessments identify sites where stream/river restoration projects will be most beneficial in order to and restore the stream/river to least erosive form over time (i.e., equilibrium condition) and improve habitat. Work includes project development and prioritization to target cost effective actions. | River |  | 58
Stream Geomorphic Assessment Phase 1 | Remote sensing assessment of rivers/streams at the watershed scale to divide rivers/streams into reaches and provide an initial review of stream reach condition. | River |  | 24
Stream Geomorphic Assessment Phase 2 | Field based assessments of stream reaches to determine current geomorphic and habitat conditions and to determine potential management needs and strategies to restore stream to least erosive form over time (i.e., equilibrium). Could be done in conjunction with a Phase 1 Stream Geomorphic Assessment. | River |  | 25
River - Education & Outreach | Developing and/or disseminating material to educate the public on water quality issues in the rivers sector and local and statewide initiatives to facilitate the protection, maintenance, enhancement, and restoration of water resources through behavioral change. | Rivers |  | 76
Road Erosion Control Inventory | Inventory of roads and/or culverts required to comply with the Municipal Roads General Permit (MRGP). Inventories identify specific road erosion and stormwater problems impacting water quality and project strategies to address those issues. Inventories will inform MRGP implementation schedules, outlining specific remediation actions to be taken over a specific time-period. | Road |  | 27
Road Project - Final Design | Final design of projects to correct road related erosion problems for gravel and paved roads and road drainage culverts (e.g., ditches, turnouts, check dams, culvert armoring) and stormwater treatment practices that collect, store, infiltrate, and filter runoff from transportation infrastructure (e.g., bioretention, gravel wetlands, wet ponds). Work includes obtaining any required permits. | Road | 2 | 59
Road Project - Identification | Identification of potential locations to implement road projects outside of a Road Erosion Control Inventory that will correct high priority road related erosion problems and/or collect, store, infiltrate, and filter runoff from transportation infrastructure. Work includes project development and prioritization to target cost effective actions. | Road |  | 63
Road Project - Implementation | Implementation of projects to correct road related erosion problems for gravel and paved roads and road drainage culverts (e.g., ditches, turnouts, check dams, culvert armoring) and stormwater treatment practices that collect, store, infiltrate, and filter runoff from transportation infrastructure (e.g., bioretention, gravel wetlands, wet ponds). | Road | 3 | 60
Road Project - Preliminary Design | Preliminary determination of feasibility and design of projects to correct road related erosion problems for gravel and paved roads and road drainage culverts (e.g., ditches, turnouts, check dams, culvert armoring) and stormwater treatment practices to collect, store, infiltrate, and filter runoff from transportation infrastructure (e.g., bioretention, gravel wetlands, wet ponds). Work includes determining landowner/ municipal interest, site/design considerations, permit needs, and overall suitability for implementing project. | Road | 1 | 29
Stormwater/Roads Equipment | Purchase of stormwater equipment with demonstrated water quality benefit to enhance/improve the application/installation of best management practices that will reduce erosion and control nutrient and sediment pollution (e.g., high efficiency street sweepers, and vacuum (vactor) trucks/trailers, hydroseeders). Requires establishment of long-term use and maintenance plan (minimum of ten years). If more than one entity, would require the establishment of an equipment share/rental program. | Road | 3 | 31
Road Project - Education & Outreach | Developing and/or disseminating material to educate the public on water quality issues in the roads sector and local and statewide initiatives to facilitate the protection, maintenance, enhancement, and restoration of water resources through behavioral change. | Roads |  | 84
Road Project - Technical Assistance | Technical support to assist individuals and/or organizations with the development of projects related to the roads sector. | Roads |  | 85
MS4 - Flow Restoration Plan | Represents a Municipal Separate Storm Sewer System (MS4) flow restoration plan and associated best management practices. | Stormwater |  | 42
MS4 - Phosphorous Control Plan | Represents a Municipal Separate Storm Sewer System (MS4) phosphorus control plan and associated best management practices. | Stormwater |  | 43
Municipal Separate Storm Sewer System | Represents a Municipal Separate Storm Sewer System (MS4) permitted community. | Stormwater |  | 41
Operational Stormwater Permit Obtainment | Design and permitting of stormwater management practice(s) to comply with Operational Stormwater Permit requirements (e.g., General Permit 3-9050 referred to as the “Three-Acre General Permit”) involving treatment of existing impervious surfaces. Project readiness for permitting can vary based on prior design work completed for the site, and 30%, 60%, and 100% design stages may not be required for all projects. | Stormwater | 2 | 100
Stormwater - Education & Outreach | Developing and/or disseminating material to educate the public on water quality issues in the stormwater sector and local and statewide initiatives to facilitate the protection, maintenance, enhancement, and restoration of water resources through behavioral change. | Stormwater |  | 79
Stormwater - Final Design | Final design of stormwater management practice(s) that collect, store, infiltrate, and filter runoff that contains nutrient and sediment pollution from hard surfaces associated with developed/urban/suburban areas. Work includes securing permit(s), operation and maintenance plans, and final stewardship agreement(s). | Stormwater | 2 | 53
Stormwater - IDDE | Illicit Discharge, Detection, and Elimination (IDDE) assessment to detect unauthorized/illicit discharges of wastewater or industrial process water into a stormwater-only drainage system. When illicit discharges are detected and confirmed, municipalities are required to address the illicit discharge, preventing wastewater or industrial process water from entering surface waters through stormwater-only infrastructure. | Stormwater |  | 37
Stormwater - Implementation | Implementation of stormwater management practice(s) that collect, store, infiltrate, and filter runoff that contains nutrient and sediment pollution from hard surfaces associated with developed/urban/suburban areas. Permits, operation and maintenance plans, and stewardship agreements(s) are in place prior to construction. | Stormwater | 3 | 54
Stormwater - Mapping and Analytical Support | Collection and analysis of geospatial data that supports and enhances planning and assessment efforts to identify and prioritize developed lands/stormwater related projects (e.g., Lidar, impervious surface mapping). Does not include research projects. | Stormwater |  | 92
Stormwater - Preliminary Design | Preliminary determination of feasibility and design of stormwater management practice(s) that collect, store, infiltrate, and filter runoff that contains nutrient and sediment pollution from hard surfaces associated with developed/urban/suburban areas. Work includes determining landowner interest, site/design considerations, permitting needs, and overall suitability for project implementation. Work must result in at least 30% design of project which includes a design concept report, topographic and boundary survey, geotechnical report, and project drawings/ specifications. | Stormwater | 1 | 3
Stormwater - Research | Projects that assist in answering a question related to stormwater treatment issues, such as developing methods to account for stormwater treatment projects, or help to identify high priority water resource protection and restoration locations. | Stormwater |  | 93
Stormwater - Technical Assistance | Technical support to assist individuals and/or organizations with the development of projects related to the stormwater sector. | Stormwater |  | 80
Stormwater Master Planning | Assessment of a geographic area (subwatershed or town) to determine where stormwater pollution is generated, and where it can be captured and removed efficiently by projects. Results in a prioritized list of projects and strategies to address/mitigate stormwater runoff, and contain recommendations to preserve natural features and functions, as well as encourage use of low impact green stormwater infrastructure. | Stormwater |  | 1
Stormwater Utility Development | Incentive payments and/or financial assistance to support development of stormwater utilities. Stormwater utilities provide a dedicated revenue source for stormwater management activities, such as the design, construction, maintenance and administration of stormwater systems, as well as best management practices and other strategies to control and reduce stormwater runoff pollution to surface waters. | Stormwater |  | 74
Wastewater - Optimization Planning | Planning to reduce effluent phosphorus loads from wastewater treatment facilities by adjusting internal operations and process control within the existing treatment works. Wastewater optimization requires operators to look toward improving internal effici | Wastewater |  | 89
Wastewater - Technical Assistance | Technical support to assist individuals and/or organizations with the development of projects related to the wastewater sector. | Wastewater |  | 81
Wetland Mapping | Wetland mapping updates to local or regional Vermont State Wetlands Inventory (VSWI) maps based on current imagery and mapping standards as defined by the Vermont Wetlands Program to identify unmapped wetlands in order to protect water quality and other wetland functions and values. | Wetland |  | 67
Wetland Restoration - Education & Outreach | Developing and/or disseminating material to educate the public on water quality issues in the wetland sector and local and statewide initiatives to facilitate the protection, maintenance, enhancement, and restoration of water resources through behavioral change. | Wetland |  | 98
Wetland Restoration - Final Design | Final design of wetland and buffer area restoration and protection projects to promote water quality benefit, encourage flood resiliency, and provide habitat benefits. Work may include securing permit(s), operation and maintenance plans, and final stewardship agreement(s). | Wetland | 2 | 56
Wetland Restoration - Identification | Assessments to identify priority wetlands and buffer areas for restoration and protection work to promote water quality benefit, encourage flood resiliency, and provide habitat benefits. Assessments involve project development and prioritization to target cost effective actions. | Wetland |  | 55
Wetland Restoration - Implementation | Implementation of wetland and buffer area restoration and protection projects to promote water quality benefit, encourage flood resiliency, and provide habitat benefits. | Wetland | 3 | 33
Wetland Restoration - Preliminary Design | Preliminary design of wetland and buffer area restoration and protection projects to promote water quality benefit, encourage flood resiliency, and provide habitat benefits. Work may include determining landowner/ municipal interest, site/design considerations, permit needs, and overall suitability for implementing project. | Wetland | 1 | 69
Wetlands - Research | Projects that assist in answering a question related to wetland restoration issues, such as developing methods to account for wetland restoration projects, or help to identify high priority water resource protection and restoration locations. | Wetlands |  | 94